## monthly_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
180802130002 | 2 | 2 | 9 | 7 | 09-done | feature | add the create vue button component poc | Add a poc page with a custom vue button component demonstrating the following: - ok hardcode the id of the button , make it part of the table - ok onclick event prints the id into the console - ok ability to perform an AJAX call after pressing the button from the parent el - ok - ability to generate the id in the yymmddHHMMSS format - ok - ability to pass the id to the back-end ajax call as the - ok - grasp the child to parent event and data flow : https://stackoverflow.com/a/40915910/65706 | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 1 | feature | 2018-08-07 17:49:41 | 006dcf0b-d15b-4532-b867-4146e686c995
180802110002 | 2 |  | 6 | 5 | 01-eval | feature | select all the txt on focus during inline-cell-edit | or consider it not part of MVP and use simply Ctrl + E short cut workaround … chck the following info-src: https://stackoverflow.com/questions/6139107/programmatically-select-text-in-a-contenteditable-html-element | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 3 | 0.1 | feature | 2018-08-07 17:16:11 | 0d2dbe46-082a-435c-aba1-01839f2458f2
180801152124 | 1 |  | 6 | 9 | 09-done | refactoring | add a check for the generated md docs to have more than 100 lines | add a check for the generated md docs to have more than 100 lines | task | ysg | 2018-08-01 14:15:36 | 2018-08-01 14:15:36.853822 | 1 | 1 | feature | 2018-08-06 18:23:47 | 11dcb452-53b9-4870-9a55-9c4660a1be2c
180517213501 | 1 |  | 4 | 9 | 02-todo | feature | implement client-side testing | By using the Mojo::Chrome module: Should be able to capture JS events: Vue induced changes on the page. | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 5 | feature | 2018-08-06 18:23:47 | 12f6689a-fa8e-4024-a693-9d1e5cd5dffc
180807172028 |  |  | 4 | 9 | 02-todo | release | release version v0.4.7 | This one is blocked by the implemention of the "Delete" from the CRUDs The version 0.4.7 will introduce the CRUDs feature ( with a small s , because basically the s would stand for search via the url parameters syntax and not via a real search UI) Mention that the CRUDs feature should be considered beta as it's size is too big compared to the available time for testing, but it will be gradually improved on the way by dog fooding and refactoring ... Update the ReadMe.md file with Usage Scenarios ... | task | unknown | 2018-08-07 17:20:28 | 2018-08-07 17:20:28 |  |  |  | 2018-08-07 18:38:06 | 13b33dd8-ad91-4183-82c6-598f71355535
180807171630 | 1 |  | 4 | 9 | 07-qas | bug | the update fails if the column is nullable | Changed behaviour to try to update to NULL aka update table set col = nul where id = <<id>> | task | unknown | 2018-08-07 17:16:30 | 2018-08-07 17:16:30 |  |  |  | 2018-08-07 18:37:27 | 25c65301-2c7e-486e-b8b2-47700bf3fc5f
180806163116 |  |  | 5 | 9 | 09-done | feature-bug | add proper error handling on insert of duplicate id's | Test by quick double-clicking the addNew button. A proper message should appear prompting to try again | task | ysg | 2018-08-06 16:30:34 | 2018-08-06 16:30:34 | 0.1 | 4 |  | 2018-08-06 21:47:14 | 2b0455c4-ffd5-4283-99c4-c022ba103d8d
180803092710 | 1 |  | 4 | 6 | 02-todo | documentation | shorten the README.md | Тhe README.md is too broad - should be shorten : - remove the installation stuff … - fix all the grammar mistakes !!! | task | ysg | 2018-08-03 09:27:42 | 2018-08-30 22:00:00 | 1 | 0.1 | documentation | 2018-08-06 21:47:49 | 2b19a882-10d5-4e02-8759-942d63b8ae2b
180806170653 |  |  | 4 | 8 | 07-qas | bug | the chaining of the "with" url params does not work | The chaining of "with" url params does not work , or it has not been implemented f probably implementation fold. For example the following query: list all the early bug issues, which are not-done. http://192.168.56.120:3000/dev_issue_tracker/list/monthly_issues?as=etable&pick=id,category,status,prio,weight,name,description&where=category-eq-bug&where=status-ne-09-done the fix for the url_params fixed this one as well .. . | task | ysg | 2018-08-06 17:01:56 | 2018-08-06 17:01:56 | 2 | 0.1 |  | 2018-08-07 22:30:15 | 2c73d462-6f0e-4fa4-b339-d10d24e1fc87
180806163114 |  |  | 5 | 9 | 09-done | feature | add keyboard scrolling via the selectability of the id's | Via the tabindex="1" code | task | ysg | 2018-08-06 16:30:32 | 2018-08-06 16:30:32 | 1 | 0.2 |  | 2018-08-06 21:47:28 | 33fe6333-ed41-4af7-9169-ab353eac431b
180806214516 | 1 |  | 5 | 9 | 07-qas | feature-bug | add select-all on tab press with the keyboard in content-editable | When one uses the mouse, nothing is selected ( aka there is no event) , yet when one uses the keyboard the whole content is selected - those faster edition is possible ... add select-all on focus in content-editable. It is just annoying to every time Ctrl + E or Ctrl + A first to select all , to go to the end , when one could start typing straight aways | task | unknown | 2018-08-06 21:45:15 | 2018-08-06 21:45:15 | 1 | 1 |  | 2018-08-07 17:20:09 | 357ddadd-601f-4666-8b6d-740a312968ef
180807184617 |  |  | 5 | 9 | 02-todo | docs | document the db-dump and the db-restore operations in the DevOps guide f | document the db-dump and the db-restore operations in the DevOps guide f | task | unknown | 2018-08-07 18:46:17 | 2018-08-07 18:46:17 |  |  |  | 2018-08-07 18:47:56 | 3ae86f77-04e6-4cb1-b689-c64af8617dc9
180807184715 |  |  | 5 | 9 | type the status ... | type the category ... | type the name ... |  | task | unknown | 2018-08-07 18:47:15 | 2018-08-07 18:47:15 |  |  |  | 2018-08-07 18:48:01 | 4b6b8c67-061d-4def-a306-ff3f5f51206b
180717013201 | 1 |  | 3 | 9 | 02-todo | bug | remove the unneeded run-logging | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-07 22:30:16 | 50a360df-2b66-4b93-a42c-3f85e388b48e
180807182904 |  |  | 4 | 8 | 02-todo | feature | add esc key listener to the content editable | pressing esc when the content editable is in focus should preserve the old value and remove the focus | task | unknown | 2018-08-07 18:29:04 | 2018-08-07 18:29:04 |  |  |  | 2018-08-07 18:30:23 | 52ac4b70-edf5-400e-8d8d-8c6f394e6867
180806125917 | 1 |  | 5 | 9 | 07-qas | feature | Change the background on the editable on focus | Change the background on the editable on focus | task | ysg | 2018-08-06 12:59:17.629376 | 2018-08-06 12:59:17.629376 | 0.5 | 0.55 |  | 2018-08-06 21:47:30 | 58564210-d843-4436-94f6-109242a5aeba
180802130001 | 2 | 3 | 5 | 7 | 09-done | feature | add the create back-end web action | Create the create.pm action and integrate within the existing integration tests | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-07 18:46:11 | 617f7bb7-d380-4c48-aa86-eddf6c00dd8c
180717013001 | 1 |  | 4 | 9 | 02-todo | refactoring | remove the run-logging | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:47 | 7fafeec5-bf5f-4ec2-98c1-36227baffeb7
180806112810 | 1 |  | 4 | 4 | 09-done | feature | add automatic addition of the update_time via trigger for all tables having the update_time attribute | add automatic addition of the update_time via trigger for all tables having the update_time attribute | task | ysg | 2018-08-06 11:15:48.325569 | 2018-08-06 11:15:48.325569 | 1 | 1.5 | feature | 2018-08-06 21:47:46 | 823e35ad-4c67-4b1d-9fd2-958475eef3e6
180806125535 | 2 |  | 2 | 9 | 03-wip | documentation | update the docs for the CREATE in CRUDS feature | Update the docs for the CREATE in CRUDS feature: - update the Features and Functionalities Guide - update the System Guide ( logic for the update ) - update the Requirements - update the UserStories | task | ysg | 2018-08-06 12:55:35.853206 | 2018-08-06 12:55:35.853206 | 3 | 1.1 |  | 2018-08-07 18:44:06 | 8de84df4-24a6-4322-8d76-d8b2b4662868
180807182818 |  |  | 5 | 9 | 07-qas | devops | create oneliner for quick db-dump | The following one-liner ... + quick definition for the db backup dirs : pg_dump -d $postgres_db_name -U ysg > $mix_data_dir/sql/pgsql/dbdumps/$postgres_db_name/$postgres_db_name.`date "+%Y%m%d_%H%M%S"`.dmp.sql ls -1 dat/sql/pgsql/dbdumps/$postgres_db_name/*.sql ¦sort # dat/sql/pgsql/dbdumps/dev_issue_tracker/dev_issue_tracker.20180807_182659.dmp.sql # dat/sql/pgsql/dbdumps/dev_issue_tracker/dev_issue_tracker.20180807_183107.dmp.sql | task | unknown | 2018-08-07 18:28:18 | 2018-08-07 18:28:18 |  |  |  | 2018-08-07 18:46:07 | 903d0ad8-5285-4a3a-aca8-0cdc5657750c
180807185440 |  |  | 1 | 9 | 02-todo | feature | add quickly the back-end for the DELETE | Add quickly the back-end for the DELETE action. because it would help out the usage of the UI ... and reduce the required time for testing ... OR at least the ok flow ... | task | unknown | 2018-08-07 18:54:40 | 2018-08-07 18:54:40 |  |  |  | 2018-08-07 22:10:29 | 909aa8ac-eb4e-455d-afa2-2c29ad2b29d6
180517213101 | 1 |  | 3 | 9 | 02-todo | load-testing | add load testing to the update back-end web action | By simply instantiating ASYNCRONOUSLY 2,4,16,32,64,128,256,512,1024 ajax calls at once non-blocking-wise . Chk the following info src: https://mojolicious.io/blog/2017/12/09/day-9-the-best-way-to-test/ http://blogs.perl.org/users/chase_whitener/2016/01/mock-testing-web-services-with-mojo.html | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 2 | feature | 2018-08-07 17:42:36 | 98e6b6fb-e165-41b6-afc8-74d86d18eec6
180802130102 | 2 | 5 | 2 | 7 | 02-todo | feature | add the delete vue button component poc | Add a poc page with a custom vue button component demonstrating the following: - ability to instantiate multiple independant instances of the button - ability to assign different id's to the buttons - ability to present dialog box with ok and cancel after the clicking of the button - ability to perform an AJAX call after pressing the button - ability to perform an AJAX call after pressing the ok | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-07 18:44:04 | 9b5f133b-71a8-48c7-a4aa-d1536f09e707
180710102901 | 1 | 1 | 4 | 8 | 07-qas | feature | add the CREATE for the CRUD table via a single click in etable | via a single click in the e-table: - wip for add the button ui - ok for click inserts into db - wip for fetch new item data | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:47 | acaa69b2-5ca9-48b5-b547-0d7dd3b49ad9
180801133401 | 1 |  | 5 | 9 | 09-done | bug | clean-up all the console.log from the list-etablet template | All the console.log statements should be cleaned | refactor | ysg | 2018-06-26 10:00:00 | 2018-06-29 11:00:00 | 4 | 0.1 | feature | 2018-08-06 21:44:12 | ad6c270e-ffd3-49e2-aa53-b01089187cc9
180806172736 |  |  | 3 | 9 | 02-todo | feature | fix the headers and the search form | The inline cell update does not probably implement the vue model and life cycle .. The table headers and the search form should stay at the top - 2% of the page | task | ysg | 2018-08-06 17:22:39 | 2018-08-06 17:22:39 | 3 | 0.1 |  | 2018-08-07 18:57:30 | b6e0db40-6aed-405d-acd2-ee77abd717ac
180802130101 | 1 | 4 | 4 | 7 | 02-todo | feature | add the delete back-end web action | delete the delete.pm action and integrate within the existing integration tests | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-07 17:16:12 | c0761c85-dc6e-4683-b9b0-a207bad5628d
180717013101 | 1 |  | 5 | 9 | 09-done | bug | fix the bug "for updating the cell content in table inline edit on error, while it shouldn't" | related to the it-180801151524 ... this is more of a generic question - how-to keep in sync the client-side and server side data structures - perhabs must update the client side array too ?!After the user updates the cell conent the post fires, the error msg is displayed but the content stays changed while it is not changed in the db … which is misleading … The behaviour should be changed so that the content will preserve its original state ... | bug | ysg | 2018-07-17 00:00:00 | 2018-07-17 02:00:00 | 50 | 8 | feature,msg | 2018-08-06 21:45:06 | cabd54d8-d56c-458c-9ce9-821561ce716a
180802105623 | 1 |  | 3 | 9 | 09-done | release | release v0.4.6 | Couple of small fixes in the integration tests ... release v0.4.6 should be considered "transitional" release as it contains only the update of the CRUDS feature, although there is some need for refactoring and additional testing the "create " and "delete" features must be added asap to avoid wasting time with additional tools and Excel. Also this should be the first release to be released to the cloud as well. | task | ysg | 2018-08-02 10:56:49 | 2018-08-05 22:56:49 | 3 | 0 | release | 2018-08-07 18:15:21 | dc91451d-460f-4092-9f6b-ae85e5ed0699
180806125916 | 1 |  | 5 | 1 | 09-done | bug | the inline-cell update removes the new lines from the cell | the inline-cell update removes the new lines from the cell ops - wrongly used ev.target.textContent when ev.target.innerText should have been used | task | ysg | 2018-08-06 12:59:16.274161 | 2018-08-06 12:59:16.274161 | 1 | 0.7 |  | 2018-08-06 21:47:33 | e3a3ff71-3133-4258-87a1-104ee13e2007
180806212213 |  |  | 9 | 9 | 07-qas | feature | add scroll till the top | related to the it-180801151524 Add scroll till the top when the table ends ... Add more space in the page Related to the | task | unknown | 2018-08-06 21:22:13 | 2018-08-06 21:22:13 | 3 | 0.3 |  | 2018-08-07 17:20:12 | e5eaf91a-b401-4a2e-acf1-c79d2892536d
180806173205 |  |  | 3 | 9 | 02-todo | bug | the sorting does not work after updating and item | It works only after refreshing the page The inline cell update does not probably implement the vue model and life cycle .. Related to the it-180806172736 issue: http://host-name:3000/dev_issue_tracker/list/monthly_issues?as=lbls&pick=id,category,status,prio,name,description,planned_hours,actual_hours&page-size=100&page-num=1&with=id-eq-180806172736 | task | ysg | 2018-08-06 17:27:08 | 2018-08-06 17:27:08 | 3.33 | 0.1 |  | 2018-08-07 22:30:50 | e872158d-3a1f-4a73-9a7e-033813a772f1
180801151524 | 1 |  | 5 | 9 | 04-diss | refactoring | No relevant anymore ... Refactor the edit web action to reflect the vue page life cycle | As shown in the following diagram:info-src: https://vuejs.org/v2/guide/instance.html#Lifecycle-Diagram | task | ysg | 2018-08-01 14:15:36 | 2018-08-01 14:15:36.853822 | 4 | 10 |  | 2018-08-06 21:41:24 | efe6fb81-aec8-4cbd-a1e6-16b18c75e623