## problems
id | level | seq | prio | weight | status | category | name | description | solution_proposal | owner | update_time | guid
1806102335 | 1 | 2 | 5 | 5 | 02-todo | setup | npm modules | the installed with npm installed modules are not transfered in the | One of those ?! : - npm install commands in the product instance install shell call ... | ysg | 2018-08-06 18:23:47 | 00458856-b96f-4d4b-a325-ec31844c64aa
1805172131 | 1 | 1 | 3 | 7 | 03-act | testing | the long term goals are quite ambitions compared to the allocated time | The scope of the application in terms of features is enourmous compared to the available allocated time ... | Try: - work smarter, not harder - attract more developers, by opennes and userfriendliness | ysg | 2018-08-06 18:23:47 | 23b855ea-b061-454a-b98e-7eef11380cd8
1805181956 | 1 | 1 | 3 | 7 | 03-wip | testing | complexity is building up ... | The more complexity is added to the system the more regression bugs occur: | More : - end-to-end testing - client side JS testing | ysg | 2018-08-06 18:23:47 | 65c22915-6d1f-4513-9c0d-9a977c2226a5
1805171359 | 1 | 1 | 4 | 5 | 03-act | performance | how-to implement minification ?! | A lot of data is lost when the code is not minified - this is also a potential financial cost ... | Some kind of Mojo::Plugin ?! Or external plugin ... | ysg | 2018-08-06 18:23:47 | 72219045-040c-42c9-8cbe-689ada2f58e2
1805312200 | 1 | 2 | 2 | 8 | 02-todo | architecture | too much msgs floating around | the amount of messages becomes overwellming , one cannot be able to manage them from a central location | - keep the ( ret , msg , whatever , else ) in list context call order ... it just works ... - keep using the msg var for a msg , but what if there are other msgs ... some kind of hash with message return code ? CallStatus type of object ?! | ysg | 2018-08-06 18:23:47 | 92ab00e9-f521-434b-a885-3dcf06439fe6
1807031157 | 1 | 2 | 5 | 5 | 03-act | architecture | documentation overbloat | The amount of the documentation becomes huge : - time consuming to keep up-to-date - who is going to read that ?! | Activate on those: - split into smaller documents - remove content which is developer oriented - they should know how-to check from the src code | ysg | 2018-08-06 18:23:47 | 9e51fbb3-e1ba-4ca1-8ef7-54522095fcd4
1805070100 | 1 | 2 | 7 | 5 | 06-onhold | architecture | the xls is crashing all the time | Ain't crashing so often when ran straight from the mac … use it as less as possible. Recreate it from scratch by copying only the data. And data is lost when the vm is put into sleep mode … | Activate on those:- run on mac- install the phppgadmi - create web json update and insert ui - enable db-to-json - json-do-db - php-admin ?! | ysg | 2018-08-06 18:23:47 | abc77ce6-2b59-46e7-b404-8d28003bee72
1706010100 | 1 | 1 | 5 | 5 | 02-todo | testing | unit controls testing | how-to unit test ui controls | Install Joe Bergers chrome | ysg | 2018-08-06 18:23:47 | b6925e6d-90c1-497e-9e12-e1dbc824c4af
1804010100 | 1 | 2 | 5 | 5 | 06-onhold | architecture | full stack architecture definition | Probably obsoleteGaps in the skills to define the full-stack architecture ... | Activate on those: - end-to-end testability | ysg | 2018-08-06 18:23:47 | c54b25e1-b80e-457c-ba31-98fae149fa64
1805010100 | 1 | 2 | 9 | 9 | 09-done | testing | how-to describe the unit tests texts | The test names and descriptions should be part of the application content, linked to the requirements and userstories. | Do not describe tests at all - tests are code and they should remain code , but do describe features and functionalities with guids. | ysg | 2018-08-06 18:23:47 | e6f23d12-1430-4165-89bb-fbda9ad8a2f0