## quinquennially_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
1806110013 | 1 |  | 5 | 5 | 03-act | ui | add dynamic switch of pre-defined ui themes | would require a totally new approach to ui design + possibly changes to the css dir structure | milestone | ysg | 2019-01-01 00:00:00 | 2020-01-01 00:00:00 | 100 | 0.1 |  | 2018-08-06 18:23:46 | 02cab5c6-72a0-473b-940b-307e4cb6759e
1806011304 | 1 |  | 5 | 5 | 03-act | org-development | attract 2 full stack developers for collaboration | attract 2 full stack developers for collaboration | goal | ysg | 2018-05-08 00:00:00 | 2020-01-01 00:00:00 | 30 | 2 | org | 2018-08-06 18:23:46 | 3757fef4-78af-4189-880d-6feeb3df0b0a
1806011303 | 1 |  | 5 | 5 | 03-act | development | get 10 starts and 5 pull requests | By achieving 10 stars and 5 pull requests | goal | ysg | 2018-06-01 00:00:00 | 2019-01-01 00:00:00 | 30 | 2 |  | 2018-08-06 18:23:46 | 3e67f35b-5496-472a-96f1-b1fee51ed939
1707200100 | 1 |  | 9 | 1 | 02-todo | feature | implement the copy by id via the back-end api from one table to another | implement the copy by id via the back-end api from one table to another | task | ysg | 2019-01-01 00:00:00 | 2018-05-07 10:26:09 | 20 | 0.2 |  | 2018-08-06 18:23:46 | 5cee88d2-1ee7-44dd-8398-56ec74e29ac0
1807031404 | 1 |  | 5 | 5 | 02-todo | ui | add hierarchichal table listing page | Add listing for the hierarchical data: - should have visual differentiation between first level and sub-levels … | milestone | ysg | 2019-06-01 00:00:00 | 2019-12-31 00:00:00 | 30 | 1 | ui | 2018-08-06 18:23:46 | 636d6a11-0c75-43ea-8856-b66bce3df1e7
1806011305 | 1 |  | 5 | 5 | 03-act | org | 20 users for issue-tracker projects | aquire more than 20 users to feed in data of issue-tracker prjojects | goal | ysg | 2018-06-01 00:00:00 | 2019-01-01 00:00:00 | 200 | 3 | org | 2018-08-06 18:23:46 | 88fec13d-3d71-471f-993f-c8c812fd9b34
1806011302 | 1 |  | 5 | 5 | 03-act | issue-tracker | minimalistic MVP with basic auth in the web | Deploy to an amzn instance : - minimalistic mvp with gruds and basic ui - basic auth - multiple projects | goal | ysg | 2018-06-01 00:00:00 | 2019-01-01 00:00:00 | 450 | 0.1 |  | 2018-08-06 18:23:46 | d3201908-eebd-4370-a81b-a59d35889046
1806011301 | 1 |  | 5 | 5 | 03-act | issue-tracker | complete secured instance in the web | complete secured instance in the web: - OAuth2 , authorization and authentication - full CRUD ui for issues,projects,problems,questions,principles - history data management - time tracking biz features | goal | ysg | 2019-01-01 00:00:00 | 2019-06-30 00:00:00 | 450 | 0.1 |  | 2018-08-06 18:23:46 | f6e7301b-96d3-4c07-9240-ed3a35bbf6af