## yearly_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
1806281842 | 2 | 2 | 9 | 9 | 09-done | feature | add Update Controller for accepting the edit REST calls | The Update Controller return the code of whether of not the update has succeeded: | task | ysg | 2018-07-01 00:00:00 | 2018-07-30 00:00:00 | 30 | 1 | setup | 2018-08-06 18:23:46 | 024a826d-2998-4ae5-bbf3-035bc0aa49d8
1806011648 | 1 | 5 | 8 | 2 | 09-done | setup | Install FE required binaries | setup nodejs, webpack and bower for Front-End development | setup | ysg | 2018-06-01 00:00:00 | 2018-06-01 00:00:00 | 2 | 2 | setup | 2018-08-06 18:23:46 | 0ac4be02-e209-4e1a-b790-aa5c22143122
1806060841 | 1 | 6 | 3 | 6 | 02-todo | testing | poc for client side testing for all the client side functionalities | Evaluate: - pure selenium - https://github.com/jhthorsen/test-mojo-role-selenium poc for client side testing for all the client side functionalities | feature | ysg | 2018-05-25 20:53:00 | 2018-06-30 00:00:00 | 10 | 7 | feature | 2018-08-06 18:23:46 | 0be434f5-1066-43dd-be7e-053de08c5447
1807101032 | 3 | 3 | 5 | 5 | 02-todo | feature | place the cursor at the end of the txt in content editable during update | chk: https://stackoverflow.com/a/19588665/65706 | feature | ysg | 2018-07-20 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 0f6686f3-1608-4e09-a546-710201280231
1805152400 | 2 | 10 | 9 | 1 | 09-done | feature | add the order-by url param for the list web control | add the order-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2018-05-14 07:00:00 | 2018-06-29 07:00:00 | 5 | 2 | feature | 2018-08-06 18:23:46 | 12190348-4e10-481b-a816-fb3f67f38a44
1807170130 | 1 | 10 | 9 | 9 | 04-fail-remove | bug-refactoring | separate the error msg | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-07 15:50:49 | 13cd0a4c-2ce6-4683-8c40-e54615116494
1806281640 | 1 | 10 | 5 | 7 | 02-todo | feature | add pages minification on deployment | Pages must be minified as 1/3 of the data is white space … | task | ysg | 2018-10-01 00:00:00 | 2018-12-30 00:00:00 | 20 | 1 | setup | 2018-08-06 18:23:46 | 162fd56d-ff0d-4171-ba3e-a0e8bce60b1c
1804290100 | 1 | 10 | 5 | 5 | 09-done | docs | fix nasty bug in Initiator cause by related dir in mojo testing framework | Or add the ability to resolve the dir structure of any perl script using the Initiator - obs has to be called only once ... fix nasty bug in Initiator cause by related dir in mojo testing framework. The root cause - the Initiator used $0 while it should have used __FILE__. See : https://stackoverflow.com/a/90721/65706 | task | ysg | 2018-04-29 10:21:23 | 2018-04-29 13:21:23 | 2 | 3 | docs | 2018-08-06 18:23:46 | 169f00ae-3217-462b-94b2-b1b811a281c8
1805110600 | 1 | 10 | 5 | 5 | 02-todo | activities | publish a read-only issue-tracker MVP to a host in the cloud for demo purposes | add link to the git-hub | activity | ysg | 2018-05-06 07:00:00 | 2018-12-31 07:00:00 | 0.1 | 0.1 |  | 2018-08-06 18:23:46 | 1749f537-2230-4f6f-af18-5b5b4c890025
180807161147 |  |  | 1 | 9 | type the status ... | type the category ... | type the name ... |  | task | unknown | 2018-08-07 16:11:47 | 2018-08-07 16:11:47 |  |  |  | 2018-08-07 16:11:47 | 19a9fcc5-64d1-4683-b725-fb6fef8d6513
1805141000 | 1 | 10 | 9 | 1 | 04-diss | docs | create user manual | create the user manual document, which will contain ONLY business rules and logic as well as non-devops related content. | docs-addition | ysg | 2018-05-25 20:53:00 | 2018-05-30 00:00:00 | 0.5 | 0.5 |  | 2018-08-06 18:23:46 | 1d2744a6-2fcd-46a5-b121-78387616c316
1805110400 | 2 | 10 | 6 | 1 | 01-eval | feature | improve the select-tables web action | Add the following: - list of views - order by table name - convert result-set to array and not hash | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 1 | 0.1 |  | 2018-08-06 18:23:46 | 20f646a7-c322-40f1-b0bf-777fff8f3e5e
1806011111 | 1 | 10 | 5 | 9 | 03-wip | architure | change Front-End architecture to use Web Pack | As Web Pack seems to be the best in town package manager and a lot of JS code is distributed as npm packages. | task | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 0.1 |  | 2018-08-06 18:23:46 | 218c1b15-0a7c-4b0b-86ca-0b5a586b7ac4
1806110034 | 1 | 10 | 6 | 7 | 02-todo | feature | add a modal dialog edit form for the edit action | Could be either from the list as html page or from the list as lables page | task | ysg | 2018-07-30 00:00:00 | 2018-08-31 00:00:00 | 30 | 0.2 |  | 2018-08-06 18:23:46 | 23c3fd72-679c-4f45-a4b0-ba33485e4bf4
1805160700 | 2 | 10 | 5 | 5 | 02-todo | feature | add the feature for the validation of the spent time | design the validation of the available time and the spent time = registered time | task | ysg | 2017-08-06 00:00:00 | 2017-08-07 00:00:00 | 15 | 0.1 |  | 2018-08-06 18:23:46 | 2576cfcb-ec09-4907-9344-344e9ea553bd
1806110038 | 1 | 5 | 7 | 1 | 09-done | setup | the client side ui sorter does not support soring by numbers | Need to implement own sorting method. This is complete no-go for correct financial data !!! | bug | ysg | 2018-06-10 21:30:00 | 2018-12-31 07:00:00 | 5 | 0.3 | setup | 2018-08-06 18:23:46 | 30243762-f0c3-4747-a573-6710f19ee71f
1806241213 | 1 | 6 | 5 | 9 | 02-todo | feature | add poc for the vue-js-modal dialog page | Add the poc from the following source: https://github.com/euvl/vue-js-modal/blob/master/README.md Probably all the node_modules must be installed globally, because there is dependency between the mojo morbo web server … which gets REAAALly SLOW … | task | ysg | 2018-06-24 00:00:00 | 2018-06-30 00:00:00 | 2 | 0.3 | poc | 2018-08-06 18:23:46 | 331aaf30-45a2-45c0-a5fa-a19b9d513aa9
1806011702 | 1 | 5 | 9 | 1 | 09-done | setup | fix bug for non-aplying multiple with url params | Root cause - simple return in the wrong way of the loop | bug | ysg | 2018-06-04 21:00:00 | 2018-06-04 22:30:00 | 0 | 1.5 | setup | 2018-08-06 18:23:46 | 36a82200-0972-4dcc-9ab0-2458c36a6d75
1807170141 | 1 | 10 | 5 | 5 | 04-fail-move-to-yearlies | documentation | document the list as table control flow in the system guide | Update the application control flow descpription | documentation | ysg | 2018-07-17 00:00:00 | 2018-07-17 02:00:00 | 50 | 8 | feature,msg | 2018-08-06 18:23:46 | 3761dfcf-91a4-427e-ad1a-f62063ff2008
1805301624 | 1 | 4 | 4 | 4 | 02-todo | issue-tracker | fix bug for the issue_tracker.pl.log appearance in product instance dir | Occurs when one runs the "run-integration-tests" action | bug | ysg | 2018-05-29 20:53:00 | 2018-06-30 00:00:00 | 0 | 0.1 | bugs | 2018-08-06 18:23:46 | 3a83bebb-7e57-4955-a744-df64f8fec4f0
1806232256 | 1 | 5 | 5 | 5 | 02-todo | feature | add modal dialog for item-edit in the list table ui | add modal dialog for item-edit in the list table ui. Status change -> 04-diss . No time till the end of this monthly … | task | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 2 | feature | 2018-08-06 18:23:46 | 3b210ebd-7a52-42f7-989f-eb02aaf119b9
1805172136 | 1 | 10 | 3 | 5 | 02-todo | deployment | deploy a web accessible instance with basic authentication for demo purposes in amzn | To be done straight after the CRUDS completion. Deploy an instance of the issue-tracker application, which will be www readable, but editable via a simple authentication. | goal | ysg | 2018-05-17 00:00:00 | 2018-12-30 00:00:00 | 20.1 | 0.1 |  | 2018-08-06 21:32:45 | 3f0d7194-c7ce-4848-8a54-1260efbd5eee
1806061000 | 1 | 6 | 9 | 1 | 02-todo | feature | add the concepts document | The Concepts document should provide the following sections: - Introduction - Mission statement - Concept illustration Status update: move to yearly. Too early for this type of docs .. Yet. | feature | ysg | 2018-06-01 00:00:00 | 2018-12-30 00:00:00 | 10 | 0.1 | feature | 2018-08-06 18:23:46 | 417cf290-bc7d-43ac-91eb-320ba5a23492
180803161926 | 1 |  | 6 | 6 | 02-todo | feature | implement a new hierarchy model | implement a new hierarchy model by using the seq into a separate items_hierarchy table , which will have the following attributes: id - the FK pointing to the items id seq - the sequence in the hierarchy item_nam e- the name of the item's table to refer to ( all those should comprise an unique PK ) Change in the hierarchy would mean changing the seq number - those not all issues will be hierarchical, but those which are could be seen in an hierarchy UI !!! | task | ysg | 2018-10-01 20:53:00 | 2018-12-31 20:53:00 | 30 | 0.1 | hierarchy | 2018-08-06 18:23:46 | 428b55bd-8ef4-4f30-9c7f-5fe29057dad9
1806011701 | 1 | 5 | 6 | 5 | 01-eval | setup | configure web-pack packaging | configure web-pack packaging Is it even feasible to have the web-pack in the current setup ?! | setup | ysg | 2018-06-01 00:00:00 | 2018-06-10 00:00:00 | 2 | 2 | setup | 2018-08-06 18:23:46 | 44fda35e-21b5-4af9-b148-1552a2fb7cf8
1806281041 | 1 | 5 | 5 | 9 | 09-done | testing | fix bug for increase-date | The increase date shell action now: - supports different sub-dirs - xls,json,txt | feature | ysg | 2018-06-28 20:53:00 | 2018-06-30 00:00:00 | 1 | 2 | bug,feature-root-cause | 2018-08-06 18:23:46 | 459ffadd-8f23-4295-b8ef-bb73e98fd5a5
1807101027 | 2 | 2 | 9 | 9 | 09-done | feature | add UPDATE for the CRUD table inline | - ok - for fragile ok case - ok - for the preserving of the new lines - ok - for the ok test - ok - for preventing the id, and guid from editing - ok - handle error on non-db - ok - handle error on non-table - ok - handle error on non-column - diss - handle error on non-id - ok - handle any other error - diss - try multiple columns | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 492139df-ee9d-4815-8ba0-df9b2b9ed206
1806231402 | 3 | 5 | 7 | 2 | 09-done | feature | add a visual indication for the active page number in the list tables view | Well, good enough for now ... Later one ... probably would need more styling ... As currently it is not exactly clear which page is the current one … The less experience is the user the more urgent this feature is … | feature | ysg | 2018-05-25 20:53:00 | 2018-06-30 00:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | 4939f666-8b0a-4450-9bb2-56537e74f60d
1807101029 | 2 | 5 | 3 | 8 | 01-eval | feature | add the DELETE for the CRUD table | via a vue-js-modal form | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 49efe9c1-8757-4850-9d72-4e4e0bf623f5
1807031419 | 1 | 5 | 9 | 9 | 09-done | setup | deploy demo instance to aws | Iterate the installation documentation. | task | ysg | 2018-07-04 04:06:05 | 2018-07-04 23:06:05 | 3 | 3 | setup | 2018-08-06 18:23:46 | 4a564c84-dd69-46ad-90fe-e1640efaba9c
180803093321 | 1 | 10 | 9 | 3 | 03-act | feature | add and automate as much as possible the deployment of a new released version to the cloud as part of the release process | add and automate as much as possible the deployment of a new released version to the cloud as part of the release process | task | ysg | 2018-09-01 12:00:00 | 2018-09-30 12:00:00 | 10 | 0.1 | setup,feature | 2018-08-07 18:14:44 | 4b2a52cd-c4b9-4248-8665-9dc0df6e9f63
1806232300 | 1 | 1 | 9 | 1 | 09-done | feature | add json-to-db shell action | Add the following tests: - ensure all the tables have a generated json file from the db-to-json action - ensure the number of elements in each json files corresponds to the number of rows in the postgres table - back and forth In order to achieve independance from the xls run-time for achieving the full CRUD, I wanto to be able to take quickly backup and restore db data from files on timely basis. | task | ysg | 2018-06-23 00:00:00 | 2018-06-30 00:00:00 | 2 | 0.1 | feature | 2018-08-06 18:23:46 | 4b2d9a6e-5a29-4365-a4db-cf9f7165ba65
1807170132 | 1 | 10 | 3 | 9 | 02-todo | bugs | remove the unneeded run-logging | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 4c720b74-7819-4128-8fa6-e63425f230cc
180806103105 |  |  | 1 | 9 | 02-todo | feature | add fetching of the meta-data in the select web-action | The meta-data could be added to the met , as the data is set in the dat of the json ... | task | ysg | 2018-09-01 00:00:00 | 2018-09-30 00:00:00 |  |  |  | 2018-08-06 18:23:46 | 4deaead1-721e-4bee-93ce-22d7e01dd511
1805221029 | 1 | 10 | 4 | 6 | 04-diss | feature | add form order in url params | The ability to order the form elements from the url ... By using the pick order and not a separate fo= ... | feature | ysg | 2018-01-01 00:00:00 | 2018-12-30 00:00:00 | 3 | 0.1 | feature | 2018-08-06 18:23:46 | 4ec67678-7532-4b72-b07d-38cfb13e834e
1805172116 | 1 | 10 | 9 | 1 | 09-done | setup | upgrade Ubuntu 17.04->17.10 | Upgrade zesty to artful: - had to pre-install the whole perl modules package bundle - had to pre-install postgres ... Althought it would have worked probably by just installing the Perl postgres related modules. | feature-implementation | ysg | 2018-05-20 19:10:00 | 2018-05-20 23:10:00 | 0.1 | 2 |  | 2018-08-06 18:23:46 | 540961a6-46ee-4943-a081-6ea7bc7f15b8
1805040100 | 1 | 10 | 9 | 1 | 09-done | feature | add the pick in url to select in db reader control flow for List.pm controller | add the pick in url to select in db reader control flow | feature-implementation-implementation | ysg | 2018-05-02 10:35:00 | 2018-06-30 00:00:00 | 5 | 7 |  | 2018-08-06 18:23:46 | 54dce9ec-1054-41cf-9bc1-3cecb02c6fd7
1806261101 | 1 | 6 | 9 | 5 | 09-done | feature | add support for multi-project data backup via the db-to-json and json-to-db actions | add support for multi-project data backup via the db-to-json and json-to-db actions. Before the data backed-up went only to the product instance dir and now to the project's mix data daily dir. | feature | ysg | 2018-06-26 10:00:00 | 2018-06-26 11:00:00 | 0 | 2 | feature | 2018-08-06 18:23:46 | 55247f93-4bd6-4b1e-8b31-6c35f8d5baab
1806281111 | 1 | 5 | 9 | 9 | 09-done | feature | fix bug with incorrectly calculated page nums | The page nums are not correctly displayed | bug | ysg | 2018-06-28 18:00:00 | 2018-06-29 18:00:00 | 1 | 0.2 | bugs | 2018-08-06 18:23:46 | 55fcc574-63fd-45a9-922e-6ddad61d1ac1
1804260100 | 1 | 10 | 4 | 6 | 09-done | docs | add the issue-tracker control flow diagram to the DevOps guide | And move it to the System Guide , which seems to be a more logical place Add it to the devops guide | task | ysg | 2017-09-21 07:00:00 | 2017-09-21 07:00:00 | 2 | 0.1 | docs | 2018-08-06 18:23:46 | 59ac746a-b143-426e-8b69-10d142ce9282
180806110417 |  |  | 2 | 9 | 02-todo | bug-feature | add error on non-existent network | basically if vue , vuetify etc. libs cannot be loaded via the cdn - aka if there is no connectivity a basic error message should be added to indicate that ... | task | ysg | 2018-08-06 10:51:54.714225 | 2018-08-06 10:51:54.714225 |  |  |  | 2018-08-07 15:46:47 | 59da9507-e762-4975-a0b0-03f6affe94be
1805112000 | 1 | 10 | 5 | 5 | 09-done | feature | add error handler for xls-to-db when postgres and db table does not exist | Some kind of proper error msg | bug | ysg | 2018-05-11 21:10:00 | 2018-06-11 19:20:31 | 3 | 0 |  | 2018-08-06 18:23:46 | 5bff873b-49fe-4d5a-be56-bbcd4c70945f
1805222246 | 1 | 10 | 5 | 5 | 09-done | feature | add the with-col=val url param | add the with-col=val url param | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 4 | 6 |  | 2018-08-06 18:23:46 | 5d5189b2-43de-4d92-a3df-7806506c5d6a
1806062254 | 1 | 5 | 9 | 9 | 04-diss-move-to-yearlies | setup | add the create-table-backups shell action | Disgard - could use the json-to-db shell action to achieve the same , or quick pgsql one-liner ad-hoc ... Which would dump every table's data into the daily dir and NOT the dat dir of the product instance dir ... Might be timely ONLY after the edit action is started for the implementation ... | feature | ysg | 2018-06-08 21:00:00 | 2018-06-25 22:30:00 | 3 | 0.1 | setup | 2018-08-06 18:23:46 | 6550ea01-532d-498b-8926-dc1c45f37823
1806110020 | 1 | 6 | 4 | 6 | 02-todo | security | add validation of ui params against SQL injections | Each time a new data param is to be parametrized till the db ... A validation must be added to it. | activity | ysg | 2018-06-10 23:00:00 | 2018-12-31 07:00:00 | 5 | 3 | security | 2018-08-06 18:23:46 | 681b3805-c434-45e2-9616-6d2c58e2aa04
1805111300 | 1 | 10 | 3 | 7 | 02-todo | feature | add the create back-end web action | Create the create.pm action and integrate within the existing integration tests | activity | ysg | 2018-05-30 07:00:00 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | 6845c2be-d505-4cde-a016-04fe751340d0
1805160800 | 2 | 10 | 9 | 1 | 09-done | feature | add the where url operator for quick sql liker filtering | add the where url operator for quick sql liker filtering | task | ysg | 2017-08-06 00:00:00 | 2017-08-07 00:00:00 | 15 | 0.1 |  | 2018-08-06 18:23:46 | 68627bf3-af35-4f8b-b607-021eceb71f17
1805071500 | 1 | 10 | 9 | 1 | 09-done | feature | add the list vue.js poc | Create a proof of concept poc page with REST api fetch from the back-end using vue.js and axiom | task | ysg | 2018-05-07 13:38:00 | 2018-05-07 13:38:01 | 2 | 3 |  | 2018-08-06 18:23:46 | 68ba04d8-c819-40ab-b963-65fe1531fcc5
1805110200 | 1 | 10 | 9 | 1 | 09-done | feature | create the list page with vue.js | Create a simple list labels view interface which will use the list web action: - evaluate both server and client side html generation and compare performance - ok add error handling for missing db - add error handling for missing table - add error handling for wrong hidable column - add error handling for wrong pickable column - add error handling for wrong filterable col - add error handling for wrong col in like | feature | ysg | 2018-05-10 20:53:00 | 2018-12-31 07:00:00 | 10 | 12 |  | 2018-08-06 18:23:46 | 69002c7e-fdd5-4547-b213-d865a8474c56
1805110401 | 1 | 10 | 5 | 5 | 04-diss | feature | add db-to-json export for all the issues tables in the integration tests | To enable later the avoidance of the xls file ... | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 4 | 0.1 |  | 2018-08-06 18:23:46 | 6d9ffb12-960a-4648-b288-9cd435838abe
1806241429 | 1 | 1 | 3 | 5 | 09-done | feature | add poc for vue modal dialog page | The modal dialog will be used for the CRUD functionality from the list table view and for the search … Seems too primitive - for example does not have the close by pressing escape | task | ysg | 2018-06-24 00:00:00 | 2018-06-30 00:00:00 | 3 | 0.7 | feature | 2018-08-06 18:23:46 | 6fd72ccb-ea9f-4bbb-924d-4cb598760a6b
1806071735 | 1 | 5 | 9 | 1 | 09-done | setup | achieve capability to export to pdf list-cloud and list-lbls pages via chrome UI | Could be done only via the Chrome UI | capability | ysg | 2018-06-04 21:00:00 | 2018-06-04 22:30:00 | 1 | 2 | setup | 2018-08-06 18:23:46 | 70830eb8-5029-4ad3-8438-ec6f225613ee
1806011256 | 1 | 10 | 5 | 5 | 01-eval | feature | implement a time report web ui page | The time report web ui page will : - fetch the daily,weekly,monthly and yearly hours - get the allocated hours per time period - calculate the registered actual hours to the went-by hours of the start of the period - calculate the diff between the actual and passed-by hours - accessible from the list/table-name/?as=table url - should be able t osort the data | feature | ysg | 2018-12-01 00:00:00 | 2018-12-31 07:00:00 | 20 | 0.1 |  | 2018-08-06 18:23:46 | 78d22cd6-864c-4219-ab1e-d29fc8b63e6a
1805140900 | 1 | 5 | 6 | 5 | 06-onhold-move-to-yearlies | feature | poc for data-load testing | As follows: At least 3 tables with at least 10 000 rows load. Because if you cannot get it right from the very beginning than you will get it never ever right. implement a poc for data-load testing with single table load to postgres with start and stop times recording Add as a non-blocking post update for start_time and stop_time | feature-implementation | ysg | 2018-05-25 20:53:00 | 2018-06-30 00:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | 7c3da050-81e0-4ac0-b74d-940415360773
1805082200 | 1 | 10 | 9 | 1 | 09-done | feature | improve integration testing | add the mysql db creation and population, add the documentation generation | feature | ysg | 2018-05-12 20:00:00 | 2018-05-12 21:00:00 | 2 | 2 |  | 2018-08-06 18:23:46 | 7ceb5f7a-e803-43ad-a3a9-eb3b7de1f2e2
1807142230 | 1 | 5 | 9 | 2 | 09-done-move-to-yearlies | testing | add a proper ui effect and (dis)appearance of the error msg | As it looks quite clumsy right now … | feature | ysg | 2018-05-25 20:53:00 | 2018-06-30 00:00:00 | 0.1 | 1 | feature | 2018-08-06 18:23:46 | 803e2652-5908-4209-99b7-ab72a02b4f9c
1805172131 | 1 | 10 | 2 | 9 | 02-todo | feature | implement data load testing | Should be single liner: - very simple - should have reliable start _time and stop_times - should be able to verify the executions times per request , request phases to keep track on performance while increasing complexity - and optionally all this by single user | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 2 | feature | 2018-08-06 18:23:46 | 8145bc77-49cf-43f9-b546-d1982c19c398
180807153752 | 2 |  | 5 | 9 | 07-qas | bug | THIS IS JUST A TEST |  | task | unknown | 2018-08-07 15:37:52 | 2018-08-07 15:37:52 |  |  |  | 2018-08-07 16:07:08 | 8284cfbe-6446-4c56-ae5e-1567d907333d
1807031421 | 1 | 6 | 9 | 5 | 09-done | setup | update installation instructions with aws deployment | update the aws instructions with aws deployment | task | ysg | 2018-07-04 04:06:05 | 2018-07-04 23:06:05 | 2 | 2 | setup | 2018-08-06 18:23:46 | 82940b36-3aea-4d5e-8d34-312c3921561e
1806251545 | 1 | 10 | 9 | 3 | 02-todo | documentation | add a component diagram | Add an official component diagram UML-wise: http://agilemodeling.com/artifacts/componentDiagram.htm | task | ysg | 2018-10-01 00:00:00 | 2018-12-31 00:00:00 | 3 | 0.1 |  | 2018-08-06 18:23:46 | 83182443-1c85-4ed2-810d-90d333d4d673
1805152300 | 2 | 10 | 9 | 1 | 09-done | feature | add the hide url param for the list web control | add the hide url param for the list web control - ok path - nok path | feature-implementation | ysg | 2018-05-14 07:00:00 | 2018-06-29 07:00:00 | 5 | 2 |  | 2018-08-06 18:23:46 | 8464f9d1-6a9e-42fe-bf2b-edfea1655927
180807161151 |  |  | 1 | 9 | type the status ... | type the category ... | type the name ... |  | task | unknown | 2018-08-07 16:11:51 | 2018-08-07 16:11:51 |  |  |  | 2018-08-07 16:11:51 | 872773cb-d638-442a-ac25-8115bf632a7f
1805202317 | 1 | 10 | 9 | 1 | 09-done | feature | separate the control and the page code | Add include directive in the page: - ok for add layout page - todo for add the control css from the control to the layout | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 5 | 3 | refactoring | 2018-08-06 18:23:46 | 88372df5-f14e-44f3-81ac-fd00275c9fad
1805152200 | 2 | 10 | 9 | 1 | 09-done | feature | add the pick url param for the list web control | add the pick url param for the list web control | feature-implementation | ysg | 2018-05-14 07:00:00 | 2018-06-29 07:00:00 | 5 | 2 |  | 2018-08-06 18:23:46 | 88848c01-3925-4dce-a474-0aa35cfdd88e
1807101030 | 2 | 4 | 5 | 5 | 02-todo | feature | add the UPDATE for the CRUD table via the vue-js-modal form | As an UI user of the issue-tracker application In order to be able to quickly edit the data of ANY item I want to be able to click on the edit button , fill in the poping-up dialog with the form of the full data of the item and clicking the Save button. | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 8a127f15-a399-452a-a530-ff64ae8f9f26
1805010100 | 1 | 10 | 5 | 5 | 02-todo | docs | add the Get.pm web app controller | The get controller will fetch a single item based on either on the id or the guid | task | ysg | 2017-09-21 07:00:00 | 2017-09-21 07:00:00 | 2 | 10.1 | docs | 2018-08-06 18:23:46 | 8d614c06-74b2-4cb1-9382-8ee7d07a59e5
1806281840 | 1 | 1 | 3 | 8 | 03-act | feature | add CRUD table | Add CRUD table - wip for UPDATE | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 100 | 8 | feature,CRUD | 2018-08-06 18:23:46 | 9202d5ed-ae9f-4fc0-a210-df9a66641f25
1804020100 | 1 | 10 | 9 | 1 | 09-done | feature | add the web select controller | add the web select controller “ - implementation code - tests - documentation additions for : -- requirements -- userstories -- tests -- features and functionalities | feature | ysg | 2018-04-02 18:00:00 | 2018-05-30 22:00:00 | 3 | 7 |  | 2018-08-06 18:23:46 | 95ab5eb7-d9aa-498a-aae1-74db1eba3bc8
1807170133 | 1 | 10 | 9 | 9 | 09-done | refactoring | improve the error msg behaviour and outlook in the site template | It just looked too clumsy. Now it looks more prefessional … | bug | ysg | 2018-07-17 00:00:00 | 2018-07-17 02:00:00 | 50 | 8 | feature,msg | 2018-08-06 18:23:46 | 95b9aead-2235-4812-b774-165e490ee6e9
180807153721 | 3 |  | 7 | 3 | 01-eval | feature | add push update to the table on db update | add push update to the table on db update This one is hard !!! It would require websockets ... as well as somekind of trigger which "knows" what is the last selected "area" of table check that area and push to the client the info to refresh !!!! | task | unknown | 2018-08-07 15:37:21 | 2018-08-07 15:37:21 |  |  |  | 2018-08-07 18:13:59 | 9bb1568f-e3fb-4830-9668-8759bc1e82eb
1806291841 | 1 | 1 | 3 | 6 | 06-onhold | feature | add columns stickiness in list as table ui | When the ui scrolls a table with page containing more items than the height of the screen the headers of the table must stick to the top of the page. Quite difficult with pure css … this one has been the best so far : https://jsfiddle.net/dPixie/byB9d/3/ | task | ysg | 2018-07-10 00:00:00 | 2018-08-30 00:00:00 | 3 | 1.5 | setup | 2018-08-06 18:23:46 | 9df5b82c-2d86-4967-8bb7-26871427a568
1807030420 | 1 | 6 | 4 | 5 | 01-eval | testing | fix the "can't call method unformatted bug" | FATAL Uncaught exception: Can't call method "unformatted" on an undefined value at /vagrant/opt/csitea/issue-tracker/issue-tracker.0.4.5.dev.ysg/src/perl/issue_tracker/lib/IssueTracker/App/IO/In/RdrXls.pm line 99. at src/perl/issue_tracker/script/issue_tracker.pl line 65. issue_tracker::__ANON__("Can't call method \"unformatted\" on an undefined value at /vag"...) called at /vagrant/opt/csitea/issue-tracker/issue-tracker.0.4.5.dev.ysg/src/perl/issue_tracker/lib/IssueTracker/App/IO/In/RdrXls.pm line 99 | bug | ysg | 2018-07-04 04:06:05 | 2018-10-31 12:00:00 | 5 | 0.5 | bugs | 2018-08-06 21:34:42 | a02d3ebc-5c89-4f71-a36e-ce1c7cc9d252
1805161613 | 2 | 10 | 9 | 1 | 09-done | feature | add the filter-by url param for the list web control | add the filter-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00:00 | 2017-06-29 07:00:00 | 5 | 2 |  | 2018-08-06 18:23:46 | a0327094-9f28-4bab-8dc6-b4c228bbaeb3
1805111100 | 1 | 10 | 7 | 8 | 01-eval | feature | add the edit web action from the list as labels page | Create the update.pm action and integrate within the existing integration tests | activity | ysg | 2018-05-30 07:00:00 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | a094afaf-b422-47b6-85d6-19b18606cf9a
1804020101 | 2 | 10 | 5 | 5 | 09-done | feature | add the web list controller | add the web list controller “ - implementation code - tests - documentation additions for : -- requirements -- userstories -- tests -- features and functionalities | feature | ysg | 2018-04-02 18:00:00 | 2018-05-02 18:00:00 | 3 | 0.1 | feature | 2018-08-06 18:23:46 | a2dd6c06-45f9-4415-ae1e-f40c83ba6041
180806102413 |  |  | 5 | 9 | type the status ... | feature | add fixing of the table header , page-sizer and the quick-search text-box on table scroll | Basically the upper part of the ui should stay fixed, while scrolling the table | task | ysg | 2018-09-01 00:00:00 | 2018-09-30 00:00:00 |  |  |  | 2018-08-06 18:23:46 | a34bcb5e-bcb2-4414-a926-427172c83781
1808012100 | 2 | 10 | 6 | 1 | 02-todo | bug | the sorting does not work after the inline cell update | list as etable -> update cell content inline -> sort by this column does not work … | task | ysg | 2017-08-06 00:00:00 | 2017-08-07 00:00:00 | 8 | 0.5 |  | 2018-08-06 18:23:46 | a3b94d22-7a86-4ef1-99ee-a4d6e3b9be97
1805111400 | 1 | 10 | 4 | 6 | 02-todo | feature | create the select-create form page | To test the create action and to start avoiding using the xls | activity | ysg | 2018-05-30 07:00:00 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | a44dda06-f709-4ed6-8ef1-c08def3fedbc
1806302301 | 1 | 5 | 5 | 5 | 09-done | feature | add support for multiple css themes | Just move the directory structure of the css's one level bellow … | refactor | ysg | 2018-06-26 10:00:00 | 2018-06-29 11:00:00 | 1 | 0.2 | feature | 2018-08-06 18:23:46 | a5764fdb-213c-488f-925d-af7f9aae440b
1805312157 | 1 | 10 | 9 | 1 | 09-done | bugs | fix bug with non-informance of missing db table on xls-to-db | when the xls sheet exists but the table not now the app quites | bug | ysg | 2018-05-10 20:53:00 | 2018-05-30 09:54:00 | 1 | 1 |  | 2018-08-06 18:23:46 | a90bef98-6b5e-4c4f-99fa-790c4f296e8c
1805070100 | 1 | 10 | 9 | 1 | 09-done | feature | add the error halding for non-existent db in List.pm controller | add the error halding for non-existent db in List.pm controller | feature-implementation-implementation | ysg | 2018-05-02 10:35:00 | 2018-06-30 00:00:01 | 0.1 | 0.25 |  | 2018-08-06 18:23:46 | acde0b8d-f8ea-428e-a1de-f8537f7d2d3c
1807101031 | 2 | 5 | 3 | 8 | 02-todo | feature | add the CREATE for the CRUD table via a single click in etable | via a single click in the e-table | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | ae1ae9c0-87bc-4384-badb-2ed8b9802c5a
1805111000 | 1 | 10 | 9 | 1 | 09-done | setup | add the pre-loading of the env shell configuration files | the run-integration tests should pre-load the configuration file of the current instance in order to match the full environment as it is run usually. Solution : The call has to be changed to : export issue_tracker_project=""; bash src/bash/issue-tracker/issue-tracker.sh -a run-integration-tests And documented the change in the DevOps guide | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-31 17:00:00 | 2 | 2 |  | 2018-08-06 18:23:46 | ae963e98-c5fc-40fe-b832-850d0b2a4bf2
1806011257 | 1 | 5 | 5 | 9 | 09-done | feature | implement a sortable list table ui | Should be able : - with alternative row backgrounds for odd and even - to choose the order of the colums as the pick - to choose which columns to hide - to list ANY db table - provide the same url params as in the list labels page to the back-end | feature | ysg | 2018-06-08 21:30:00 | 2018-12-31 07:00:00 | 20 | 3 | feature | 2018-08-06 18:23:46 | b05cb51f-b4d0-4257-a3f6-ba1a8611370a
1806011703 | 1 | 5 | 5 | 5 | 09-done | feature | add the "like" operator in the "where" url parameter | The like operator would select rows as follows: - where=<<column>>-<<operator>>-<<value>> , | feature | ysg | 2018-06-05 13:00:00 | 2018-06-05 14:00:00 | 0.1 | 1.5 | feature | 2018-08-06 18:23:46 | b088632b-1da1-4394-8a5f-e33d34fbc2e4
1806232301 | 1 | 10 | 9 | 9 | 09-done | feature | add json-to-db shell action | In order to achieve independance from the xls run-time for achieving the full CRUD, I wanto to be able to take quickly backup and restore db data from files on timely basis. | task | ysg | 2018-06-23 00:00:00 | 2018-06-30 00:00:00 | 2 | 0.1 | feature | 2018-08-06 18:23:46 | b0c27b86-6a5d-4c52-9309-489be31976b4
1707200100 | 1 | 10 | 9 | 1 | 02-todo | feature | implement the copy by id via the back-end api from one table to another | implement the copy by id via the back-end api from one table to another | task | ysg | 2019-01-01 00:00:00 | 2019-01-01 00:00:00 | 20.1 | 0.1 |  | 2018-08-06 18:23:46 | b13a4e70-f5da-4280-bdc4-1f5f6e138faf
1805102300 | 1 | 10 | 5 | 5 | 02-todo | feature | add a default route for the "/" web address | add a default route for the "/" web address. May be something like forward to the list view ?! | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 2 | 1 | feature, | 2018-08-06 18:23:46 | b25dbe49-ff4a-489a-a78d-2fe4dddb7a59
180806213141 |  |  | 5 | 7 | 01-eval | feature | add Excel like moving with the keys also move and down with the cursor keys | add Excel like moving with the keys also move and down with the cursor keys | task | unknown | 2018-08-06 21:31:40 | 2018-08-06 21:31:40 |  |  |  | 2018-08-07 18:14:02 | b33291c0-9311-4c64-815c-31dde6ee6779
1804300100 | 1 | 10 | 9 | 1 | 09-done | specs | define REST API response structure | Should support messages and return codes as well as data transfer. Defined : - ret - containing the http status code - msg - the msg to be passed to the client - dat - the data to be passed to the client | specs | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 1 | 2 |  | 2018-08-06 18:23:46 | b4d7587a-5f5a-4633-a30f-0c2fada05ace
1806232302 | 1 | 10 | 5 | 5 | 02-todo | feature | evaluate a lib for the generic forms creation | The CRUD functionality will require a generic forms creation | task | ysg | 2018-06-30 00:00:00 | 2018-07-15 00:00:00 | 5 | 0.3 | poc | 2018-08-06 18:23:46 | b59ddf99-8f16-422e-9500-1949caab4f90
180806110235 | 1 |  | 5 | 2 | 09-done | feature | change the accuracy of the date-time in the start_time, stop_time to seconds | change the accuracy of the date-time in the start_time, stop_time to seconds and not tics as it is simply annoying to change them by hand and the tics are not human readable ... | task | ysg | 2018-08-06 10:50:12 | 2018-08-06 10:50:12.603165 |  |  |  | 2018-08-07 15:47:09 | b61c735f-8990-4c48-9aa2-b92f7b249069
1805301337 | 1 | 10 | 6 | 4 | 09-done | bug | fix the NULL.md generated in generate-docs action | Due to the non availability of the relative path | bug | ysg | 2018-05-28 20:53:00 | 2018-05-30 00:00:00 | 2 | 3 |  | 2018-08-06 18:23:46 | b6d9005a-525d-4288-88d8-9fb561f5f105
1805102000 | 1 | 10 | 9 | 1 | 09-done | bugs | fix bug with non-publishing to google sheets | Due to the non-complience of the googleSheets controller with the Input-Output-Controller-Model architecture | bug | ysg | 2018-05-10 20:53:00 | 2018-05-30 09:54:00 | 0 | 1 |  | 2018-08-06 18:23:46 | b75ff3e1-7b19-442e-95fc-6e91ce189cc3
1805130100 | 1 | 10 | 9 | 1 | 09-done | feature | add the hide, which should pick the columns' values but not display them in the result set | add the hide, which should pick the columns' values but not display them in the result set | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 4 | 7 |  | 2018-08-06 18:23:46 | b9ccfc89-a16a-426f-b325-d92ad47cb04e
1806062253 | 1 | 10 | 9 | 1 | 04-diss | setup | poc for print-to-pdf via headless chrome | Could be achieved via UI , not so often used - no sence to spend time automating it … at least for now … | bug | ysg | 2018-06-04 21:00:00 | 2018-06-04 22:30:00 | 3 | 1 |  | 2018-08-06 18:23:46 | b9f0becc-db54-4638-b8d2-daf3b5c4c281
1806251101 | 1 | 10 | 6 | 3 | 01-eval | feature | speed-up the xls-to-db action | By running in sequence read xls , file, write to db for each table | task | ysg | 2018-07-01 00:00:00 | 2018-07-01 00:00:00 | 2 | 0.1 | feature,xls | 2018-08-06 18:23:46 | bbe11026-4a14-4900-bc80-fa826f296e4d
1807101028 | 2 | 5 | 3 | 8 | 02-todo | feature | add the CREATE for the CRUD table via a vue-js-modal form | via a vue-js-modal form | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | bdcef54c-dda3-4c6a-861b-e17b73d8e9e3
1805120100 | 1 | 10 | 9 | 1 | 09-done | specs | change the id's naming convention to be to hour proximity and not day only | As the day seems to be too less ... As the id's must be copieable from one table to another and quickly collisions might be created. | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 20:53:00 | 2 | 1 |  | 2018-08-06 18:23:46 | be016af9-919b-46cb-b1e7-51ef63e7b1b4
1805110201 | 1 | 10 | 5 | 5 | 09-done | feature | create the plain list labels view ui with vue.js | Create a simple list labels view interface which will use the list web action: - evaluete both server and client side html generation and compare performance | feature | ysg | 2018-05-10 20:53:00 | 2018-12-31 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | be547364-3ed7-43f2-a92f-0df3e6fbddc4
1805110300 | 1 | 10 | 5 | 5 | 03-act | activities | aim to use the issue tracker more on the web interface and less on the xls | In order to increase the dog food experience and provide base for the creation of issues , userstories , requirements and other specifications | activity | ysg | 2018-05-06 07:00:00 | 2018-12-31 07:00:00 | 0.1 | 0.1 |  | 2018-08-06 18:23:46 | bf1cc98e-6e1c-4615-93cc-643b4a64dd4c
180806102543 |  |  | 5 | 9 | 02-todo | feature | add vue calendar on the dates | Basically a good calendar control should be pretty easy to be integrated ... , but it would require "infra" for fetching the meta-data as well ... | task | ysg | 2019-01-01 00:00:00 | 2019-01-01 00:00:00 |  |  |  | 2018-08-06 18:23:46 | bf2206c2-0b12-415f-90a0-d008b0d6913a
1807030408 | 1 | 5 | 6 | 3 | 09-done | testing | convert the start_time and stop_time attributes to datetime format | The text format was justified for agility in the beginning , but now with the existing of so much data it is not justified anymore.Need to ensure that the | task | ysg | 2018-07-04 04:06:05 | 2018-07-04 04:06:05 | 3 | 0.1 | feature | 2018-08-06 18:23:46 | c40550e3-97cf-4ced-9b43-8aab2c13f109
1806092324 | 1 | 5 | 6 | 5 | 09-done | feature | add server side paging for the list-table ui action | Add server side paging with callable page size , and page number, limit: - todo automated ui testing - ok for UI testing - ok add a dummy page sizes list of links setting the size to the num displaed , BUT going always to the first page - create test table - ok default page size - 15 - ok for default page num - 1 | task | ysg | 2018-06-08 21:30:00 | 2018-10-30 00:00:00 | 20 | 10 | architecture | 2018-08-06 18:23:46 | c52f0e1b-0dfa-4a3f-8127-2ad13eb1693e
1806231403 | 3 | 5 | 9 | 1 | 09-done | feature | add a visual indication for the active page SIZE in the list tables view | Well, good enough for now ... Later one ... probably would need more stylingAs currently it is not exactly clear which page is the current one … The less experience is the user the more urgent this feature is … | feature | ysg | 2018-05-25 20:53:00 | 2018-06-30 00:00:00 | 2 | 0.1 | feature | 2018-08-06 18:23:46 | c5fc532a-4c4a-4dcc-aa8a-1f2d8c4f8d5a
1806061109 | 1 | 6 | 9 | 1 | 09-done | feature | refactor list web action to support multiple output types | From now on the syntax for list?as=<<output-type>> would support multiple page builders for multiple output types. The same approach could be provided to the following future web actions: - view , - edit , - create - search | feature | ysg | 2018-06-06 09:30:00 | 2018-06-06 11:30:00 | 2 | 8 | feature | 2018-08-06 18:23:46 | cabcdd3b-2303-45ad-8399-5655e89ec6e0
1806071734 | 1 | 5 | 5 | 5 | 09-done | setup | create scalable css dir structure for screen and print | This will enable the definition of printable css styles completely independent from the desktop print styles … - for now only print and screen are supported ... - probably a new level for mobile / tablets would be needed ... | bug | ysg | 2018-06-04 21:00:00 | 2018-06-04 22:30:00 | 1 | 2 | feature | 2018-08-06 18:23:46 | cc9ebc4c-6c53-4bb9-9b29-17665af6c421
1805172115 | 1 | 10 | 9 | 1 | 09-done | feature | poc for client site JavaScript testing | Because if you cannot get it right from the very beginning than you will get it never ever right. implement a poc for data-load testing with single table load to postgres with start and stop times recording Add as a non-blocking post update for start_time and stop_time. Had to increase the whole OS and redo the setup install for the perl modules and the postgres because of this one ... | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 4 | 0.5 |  | 2018-08-06 18:23:46 | cd070b3f-ee6a-4ff5-8ad5-9dcf817ec89b
1806110059 | 1 | 5 | 6 | 5 | 01-eval | feature | add the weight-by-<<attribute-name>> for the list cloud page | This would enable for example the visualization of the sizes based on actual hours , planned hours ... | feature | ysg | 2018-07-04 04:06:05 | 2018-07-04 04:06:05 | 3 | 0.1 | feature | 2018-08-06 18:23:46 | cfb65b19-88d6-439c-810e-a243bc1b94bc
1806262001 | 1 | 5 | 9 | 9 | 09-done | feature | refactor, update docs, features - regression tests walktrough | Prepare for stable monthly release - v0.4.5 | refactor | ysg | 2018-06-26 10:00:00 | 2018-06-29 11:00:00 | 4 | 0.1 | feature | 2018-08-06 18:23:46 | d0874fda-e35a-4049-8345-e2a2f0d23091
1805172135 | 1 | 10 | 2 | 9 | 02-todo | feature | implement client-side testing | By using the Mojo::Chrome module: Should be able to capture JS events: Vue induced changes on the page. | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 5 | feature | 2018-08-06 18:23:46 | d1831d21-c0f0-428e-aee3-c7346e82e3f2
1805110500 | 1 | 10 | 9 | 1 | 09-done | feature | add the like-by and like-val in url to implement the like operator for filtering | add the like-by and like-val in url to implement the like operator for filtering | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:00 | 5 | 3 |  | 2018-08-06 18:23:46 | d2da9c89-3711-44be-a52f-4abe463794f3
1806011258 | 1 | 5 | 5 | 5 | 09-done | bug | fix bug with column orders | The column order is shuffling depending on whether or not one choses the pick or leaves the pick url param ... | bug | ysg | 2018-06-10 23:56:00 | 2018-06-20 00:00:00 | 1 | 0.3 | bug | 2018-08-06 18:23:46 | daa406e5-55ba-432b-971e-ba4ff1f4ba81
1806062255 | 1 | 5 | 5 | 5 | 09-done | setup | add the phppgadmin to the configurtion setup | Installed and documented the installation - this starts the solution of the crashing xls problem which is a blocker. | setup | ysg | 2018-06-08 14:00:00 | 2018-06-08 16:00:00 | 0 | 2 | setup | 2018-08-06 18:23:46 | e3ea4cd4-1ef6-4f1e-ba15-f7d0c5636369
1805060100 | 1 | 10 | 9 | 1 | 09-done | feature | add the order-by in url to order by in db reader control flow in List.pm controller | add the order-by in url to order by in db reader control flow in List.pm controller. Changed the format of the dat to array reference because of the need to be able to pass a sorted data structure to the render json method. | feature-implementation | ysg | 2018-05-10 20:53:00 | 2018-05-30 00:00:01 | 4 | 3 |  | 2018-08-06 18:23:46 | e79a6d8e-0f86-412a-ac4c-95e6f83c1ba0
1807170131 | 1 | 10 | 9 | 9 | 09-done | bugs | fix the bug "for updating the cell content in table inline edit on error, while it shouldn't" | this is more of a generic question - how-to keep in sync the client-side and server side data structures - perhabs must update the client side array too ?!After the user updates the cell conent the post fires, the error msg is displayed but the content stays changed while it is not changed in the db … which is misleading … The behaviour should be changed so that the content will preserve its original state ... | bug | ysg | 2018-07-17 00:00:00 | 2018-07-17 02:00:00 | 50 | 8 | feature,msg | 2018-08-06 18:23:46 | e93b1a24-b512-4b33-808f-cd5f22e13add
1806091100 | 1 | 4 | 9 | 5 | 09-done | bug | fix bug for non-arranging the column in the list labels as specified in the pick order | Due to false logic in the implementation | bug | ysg | 2018-05-30 20:53:00 | 2018-06-09 10:00:00 | 1 | 0.2 | bugs | 2018-08-06 18:23:46 | e9b20874-18f8-46ba-ab6b-7708876c4af7
1805091300 | 2 | 10 | 6 | 4 | 02-todo | feature | create the view doc ui with vue.js | Create a simple list labels view interface which will use the list web action: - evaluete both server and client side html generation and compare performance | feature | ysg | 2018-05-12 20:00:00 | 2018-12-31 07:00:00 | 0.1 | 0.1 |  | 2018-08-06 18:23:46 | ea3aaf3c-ef88-4faf-9727-fac91782f71a
180806102235 |  |  | 5 | 9 | 01-eval | feature | add 3D effect on the table cells | add 3D effect on the table cells. | task | ysg | 2018-08-07 00:00:00 | 2018-08-07 00:00:00 |  |  |  | 2018-08-06 18:23:46 | ebedd47d-831e-4dda-a34d-aa15e9dc18b5
1805282138 | 1 | 10 | 5 | 5 | 02-todo | feature | add export to txt from web ui | add export to txt from web ui | feature-implementation | ysg | 2018-01-01 00:00:00 | 2018-12-30 00:00:00 | 4 | 0.1 |  | 2018-08-06 18:23:46 | ed426826-27f6-4442-bc36-7e85261d1f62
180806212921 |  |  | 1 | 9 | 02-todo | feature | develop basic authentication setup | Develop a per Issue-Tracker instance basic authentication If easy develop a per db authentication .... | task | unknown | 2018-08-06 21:29:19 | 2018-08-06 21:29:19 | 2 | 0.1 |  | 2018-08-07 18:14:07 | ed980933-5f7d-4f35-9bf6-d82e94d4ba83
1806081610 | 1 | 10 | 5 | 5 | 04-diss | feature | add omnibox poc page with web service for projects search | To be moved to the next month. add omnibox poc page with web service for projects search. The end goal should be pop-up omnibox which will present the results on enter lepton like... | poc-feature | ysg | 2018-08-01 00:00:00 | 2018-08-31 00:00:00 | 3 | 2.5 |  | 2018-08-06 18:23:46 | f03e0d83-f1ba-4ca2-9c4b-3a4ee570dff5
180807161137 |  |  | 1 | 9 | type the status ... | type the category ... | type the name ... |  | task | unknown | 2018-08-07 16:11:37 | 2018-08-07 16:11:37 |  |  |  | 2018-08-07 16:11:37 | f2d416a0-c99f-4b09-9653-34d060fcdc48
1805111200 | 1 | 10 | 4 | 6 | 02-todo | feature | add the select-update form page | To test the update action and to start avoiding using the xls | activity | ysg | 2018-05-30 07:00:00 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 18:23:46 | f3951bd2-0bb8-49bc-b680-b99ee8a670c2
1805050102 | 1 | 10 | 9 | 1 | 09-done | feature | add the filter-by in url to where in db reader control flow for List.pm controller | add the filter-by in url to where in db reader control flow for List.pm controller: - ok for ok case - add nok for col does not exist | feature-implementation-implementation | ysg | 2018-05-02 10:35:53 | 2018-06-30 00:00:00 | 7 | 6 |  | 2018-08-06 18:23:46 | f3b6a5cf-60af-4321-9997-48464ea4f3e6
1805282137 | 1 | 10 | 9 | 1 | 04-diss | feature | add export to xls from web ui | add export to xls from web ui | feature-implementation | ysg | 2018-01-01 00:00:00 | 2018-12-30 00:00:00 | 4 | 0.1 |  | 2018-08-07 15:50:40 | f4f24c13-415e-4f75-b28c-a795cc074268
1806281841 | 2 | 2 | 9 | 9 | 09-done | feature | add CRUD table control POC with dummy console.log calls | So that only the UI interface events will be captured … | task | ysg | 2018-07-01 00:00:00 | 2018-07-30 00:00:00 | 30 | 1 | setup | 2018-08-06 18:23:46 | f5942e49-4d52-455a-902e-712f16a7a4db
1805242250 | 1 | 6 | 9 | 6 | 09-done | feature | create a tag cloud page | Should increaese the ability to comprehend the issues. http://mistic100.github.io/jQCloud/demo.html - refactor to factory design pattern ... | feature | ysg | 2018-06-01 00:00:00 | 2018-12-30 00:00:00 | 10 | 8 | feature | 2018-08-06 18:23:46 | f75c030d-620d-44d1-a426-f038e51c85cf
1805161614 | 2 | 10 | 9 | 1 | 09-done | feature | add the like-by url param for the list web control | add the like-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00:00 | 2017-06-29 07:00:00 | 5 | 2 |  | 2018-08-06 18:23:46 | f98d0280-a3b7-4632-aaab-feba8f0eed56
1805050100 | 1 | 10 | 9 | 1 | 09-done | feature | add the filter-by in url to where in db reader control flow for List.pm controller | add the filter-by in url to where in db reader control flow for List.pm controller: - ok for ok case - add nok for col does not exist | feature-implementation-implementation | ysg | 2018-05-02 10:35:00 | 2018-06-30 00:00:00 | 7 | 6 |  | 2018-08-06 18:23:46 | fabe5107-ebcf-4ebe-869c-dc5e86e160f6
180807153751 |  |  | 1 | 9 | 02-todo | bug-feature | remove the restriction for default values in non-null attributes | As the current UI does not support a form for the performing of the insert , but the insert straight away inserts a default value , the clicking of the insert button always succeeds ( as the default values are provided by the database ) This one might be added once the meta-data handling has been implemented as well ... aka it might be blocked by the meta-data retrieval issue ... | task | unknown | 2018-08-07 15:37:51 | 2018-08-07 15:37:51 |  |  |  | 2018-08-07 15:50:02 | fe1eeae3-5fb4-46df-b1de-6b62d9229be6
1807162248 | 3 | 5 | 6 | 4 | 01-eval | feature | add the clone with new id html row for table for CREATE | chk the following answer: - wip add the default values for all the non-null columns - wip create the front-end call by (new Date()).toISOString().replace(/-/g,"").replace(/T/g,"").replace(/:/g,"").slice(2,14) | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 18:23:46 | fe3ca692-b9e2-409a-bc77-a246b31ac7d2