## monthly_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
1805242250 | 1 | 6 | 3 | 5 | 07-qas | feature | create a tag cloud page | Should increaese the ability to comprehend the issues. http://mistic100.github.io/jQCloud/demo.html - refactor to factory design pattern ... | feature | ysg | 2018-06-01 | 2018-12-30 | 10 | 8 | feature | 2018-06-28 09:56:36 | 0a1347cc-0e4e-4570-81fd-757569697ab5
1806011702 | 1 | 5 | 9 | 1 | 09-done | setup | fix bug for non-aplying multiple with url params | Root cause - simple return in the wrong way of the loop | bug | ysg | 2018-06-04 21:00 | 2018-06-04 22:30 | 0 | 1.5 | setup | 2018-06-28 09:56:36 | 0ee76fac-be8d-4755-aa5a-103d38256322
1806060841 | 1 | 5 | 1 | 9 | 03-wip | testing | poc for client side testing for all the client side functionalities | Evaluate: - pure selenium - https://github.com/jhthorsen/test-mojo-role-selenium poc for client side testing for all the client side functionalities | feature | ysg | 2018-05-25 20:53 | 2018-06-30 00:00 | 10 | 7 | feature | 2018-06-28 09:56:36 | 10f690a1-6b04-4e91-abb8-bccf9cf2e7cc
1806011257 | 1 | 5 | 5 | 7 | 07-qas | feature | implement a sortable list table ui | Should be able : - with alternative row backgrounds for odd and even - to choose the order of the colums as the pick - to choose which columns to hide - to list ANY db table - provide the same url params as in the list labels page to the back-end | feature | ysg | 2018-06-08 21:30 | 2018-12-31 07:00 | 20 | 3 | feature | 2018-06-28 09:56:36 | 14119b2c-b943-4205-91a3-e96905ee6bf7
1806091100 | 1 | 4 | 5 | 5 | 09-done | issue-tracker | fix bug for non-arranging the column in the list labels as specified in the pick order | Due to false logic in the implementation | bug | ysg | 2018-05-30 20:53 | 2018-06-09 10:00 | 1 | 0.2 | bugs | 2018-06-28 09:56:36 | 1678d703-5173-4de2-b48b-6669612a7e98
1806062254 | 1 | 5 | 9 | 9 | 04-diss | setup | add the create-table-backups shell action | Disgard - could use the json-to-db shell action to achieve the same , or quick pgsql one-liner ad-hoc ... Which would dump every table's data into the daily dir and NOT the dat dir of the product instance dir ... Might be timely ONLY after the edit action is started for the implementation ... | feature | ysg | 2018-06-08 21:00 | 2018-06-25 22:30 | 3 | 0.1 | setup | 2018-06-28 09:56:36 | 2e22ba2e-6047-4a3e-8f7b-df7b48644e6e
1806011258 | 1 | 5 | 5 | 5 | 09-done | bug | fix bug with column orders | The column order is shuffling depending on whether or not one choses the pick or leaves the pick url param ... | bug | ysg | 2018-06-10 23:56 | 2018-06-20 | 1 | 0.3 | bug | 2018-06-28 09:56:36 | 343e434f-574d-4166-87a3-5ce4ec85baa0
1806071735 | 1 | 5 | 9 | 1 | 09-done | setup | achieve capability to export to pdf list-cloud and list-lbls pages via chrome UI | Could be done only via the Chrome UI | capability | ysg | 2018-06-04 21:00 | 2018-06-04 22:30 | 1 | 2 | setup | 2018-06-28 09:56:36 | 34c806fc-8e02-4910-8c48-e923c283ce3f
1806261101 | 1 | 5 | 2 | 9 | 07-qas | feature | add support for multi-project data backup via the db-to-json and json-to-db actions | add support for multi-project data backup via the db-to-json and json-to-db actions. Before the data backed-up went only to the product instance dir and now to the project's mix data daily dir. | feature | ysg | 2018-06-26 10:00 | 2018-06-26 11:00 | 0 | 1 | feature | 2018-06-28 09:56:36 | 43ae450b-723e-462c-87d2-0825b3b01e14
1806071734 | 1 | 5 | 5 | 5 | 09-done | setup | create scalable css dir structure for screen and print | This will enable the definition of printable css styles completely independent from the desktop print styles … - for now only print and screen are supported ... - probably a new level for mobile / tablets would be needed ... | bug | ysg | 2018-06-04 21:00 | 2018-06-04 22:30 | 1 | 2 | feature | 2018-06-28 09:56:36 | 4b96e6cf-88ca-48df-a4cb-2618b032c503
1806061000 | 1 | 6 | 5 | 1 | 01-eval | feature | add the concepts document | The Concepts document should provide the following sections: - Introduction - Mission statement - Concept illustration | feature | ysg | 2018-06-01 | 2018-12-30 | 10 | 0.1 | feature | 2018-06-28 09:56:36 | 516e87bb-faf3-4b0d-a119-586ce04ea815
1805140900 | 1 | 5 | 5 | 5 | 06-onhold | feature | poc for data-load testing | As follows: At least 3 tables with at least 10 000 rows load. Because if you cannot get it right from the very beginning than you will get it never ever right. implement a poc for data-load testing with single table load to postgres with start and stop times recording Add as a non-blocking post update for start_time and stop_time | feature-implementation | ysg | 2018-05-25 20:53 | 2018-06-30 00:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | 5906ef78-4879-4760-9b3c-cd8532f3833d
1806241429 | 1 | 1 | 2 | 5 | 09-done | feature | add poc for vue modal dialog page | The modal dialog will be used for the CRUD functionality from the list table view and for the search … Seems too primitive - for example does not have the close by pressing escape | task | ysg | 2018-06-24 | 2018-06-30 | 3 | 0.7 | feature | 2018-06-28 09:56:36 | 6468f1d6-e722-4e6b-83b2-49388cca8643
1806110038 | 1 | 5 | 7 | 1 | 09-done | setup | the client side ui sorter does not support soring by numbers | Need to implement own sorting method. This is complete no-go for correct financial data !!! | bug | ysg | 2018-06-10 21:30 | 2018-12-31 07:00 | 5 | 0.3 | setup | 2018-06-28 09:56:36 | 6faafcd9-f998-4d6c-b1ad-1cb496d5cb1a
1806011703 | 1 | 5 | 5 | 5 | 09-done | feature | add the "like" operator in the "where" url parameter | The like operator would select rows as follows: - where=<<column>>-<<operator>>-<<value>> , | feature | ysg | 2018-06-05 13:00 | 2018-06-05 14:00 | 0.1 | 1.5 | feature | 2018-06-28 09:56:36 | 75db90c7-1321-48b1-99d9-b96f5f7def85
1806062253 | 1 | 5 | 9 | 1 | 04-diss | setup | poc for print-to-pdf via headless chrome | Could be achieved via UI , not so often used - no sence to spend time automating it … at least for now … | bug | ysg | 2018-06-04 21:00 | 2018-06-04 22:30 | 1 | 2.5 | setup | 2018-06-28 09:56:36 | 8a261d09-5915-49c0-b783-d87c6ff32eda
1805301624 | 1 | 4 | 6 | 6 | 02-todo | issue-tracker | fix bug for the issue_tracker.pl.log appearance in product instance dir | Occurs when one runs the "run-integration-tests" action | bug | ysg | 2018-05-29 20:53 | 2018-06-30 00:00 | 0 | 0.1 | bugs | 2018-06-28 09:56:36 | 8d644a91-3029-4711-b6ad-b47cf440558a
1806092324 | 1 | 5 | 5 | 5 | 07-qas | feature | add server side paging for the list-table ui action | Add server side paging with callable page size , and page number, limit: - todo automated ui testing - ok for UI testing - ok add a dummy page sizes list of links setting the size to the num displaed , BUT going always to the first page - create test table - ok default page size - 15 - ok for default page num - 1 | task | ysg | 2018-06-08 21:30 | 2018-10-30 | 20 | 10 | architecture | 2018-06-28 09:56:36 | 95a53237-7f60-4f27-afc6-4f656bcefd62
1806231403 | 3 | 5 | 5 | 4 | 02-todo | feature | add a visual indication for the active page SIZE in the list tables view | As currently it is not exactly clear which page is the current one … The less experience is the user the more urgent this feature is … | feature | ysg | 2018-05-25 20:53 | 2018-06-30 00:00 | 2 | 0.1 | feature | 2018-06-28 09:56:36 | 9da1b1e1-0201-424b-9464-704e94059016
1806110020 | 1 | 5 | 3 | 6 | 03-act | security | add validation of ui params against SQL injections | Each time a new data param is to be parametrized till the db ... A validation must be added to it. | activity | ysg | 2018-06-10 23:00 | 2018-12-31 07:00 | 5 | 3 | security | 2018-06-28 09:56:36 | ad1d1dbb-ad3b-4692-8357-8f8e3fff3a32
1806110059 | 1 | 5 | 5 | 5 | 02-todo | testing | add the weight-by-<<attribute-name>> for the list cloud page | This would enable for example the visualization of the sizes based on actual hours , planned hours ... | feature | ysg |  |  | 3 | 0.1 | feature | 2018-06-28 09:56:36 | b1d599f6-f0cc-4959-882c-c9fdab4ed066
1806241213 | 1 | 1 | 2 | 9 | 02-todo | feature | add poc for the vue-js-modal dialog page | Add the poc from the following source: https://github.com/euvl/vue-js-modal/blob/master/README.md | task | ysg | 2018-06-24 | 2018-06-30 | 2 | 0.3 | poc | 2018-06-28 09:56:36 | b6f0dc50-c0d6-4252-831f-e052da41d72b
1806011648 | 1 | 5 | 8 | 2 | 09-done | setup | Install FE required binaries | setup nodejs, webpack and bower for Front-End development | setup | ysg | 2018-06-01 | 2018-06-01 | 2 | 2 | setup | 2018-06-28 09:56:36 | c353551b-56b0-4a56-8e40-2ee10e423a10
1806062255 | 1 | 5 | 5 | 5 | 09-done | setup | add the phppgadmin to the configurtion setup | Installed and documented the installation - this starts the solution of the crashing xls problem which is a blocker. | setup | ysg | 2018-06-08 14:00 | 2018-06-08 16:00 | 0 | 2 | setup | 2018-06-28 09:56:36 | c50d9e53-8b11-4019-bce1-23e7029980b3
1806011701 | 1 | 5 | 5 | 5 | 06-onhold | setup | configure web-pack packaging | configure web-pack packaging | setup | ysg | 2018-06-01 | 2018-06-10 | 2 | 2 | setup | 2018-06-28 09:56:36 | c9cfb11f-30e4-4f27-899d-e9acc9838467
1806232256 | 1 | 5 | 4 | 6 | 01-eval | feature | add modal dialog for item-edit in the list table ui | add modal dialog for item-edit in the list table ui | task | ysg | 2018-06-01 | 2018-07-30 | 50 | 2 | feature | 2018-06-28 09:56:36 | caa1e324-de4d-418e-b30e-a51c2981e623
1806232301 | 1 | 1 | 5 | 6 | 07-qas | feature | add json-to-db shell action | Add the following tests: - ensure all the tables have a generated json file from the db-to-json action - ensure the number of elements in each json files corresponds to the number of rows in the postgres table - back and forth In order to achieve independance from the xls run-time for achieving the full CRUD, I wanto to be able to take quickly backup and restore db data from files on timely basis. | task | ysg | 2018-06-23 | 2018-06-30 | 2 | 0.1 | feature | 2018-06-28 09:56:36 | d54020ad-c295-4ac6-8e37-afdf40aedd78
1806061109 | 1 | 6 | 9 | 1 | 09-done | feature | refactor list web action to support multiple output types | From now on the syntax for list?as=<<output-type>> would support multiple page builders for multiple output types. The same approach could be provided to the following future web actions: - view , - edit , - create - search | feature | ysg | 2018-06-06 09.30 | 2018-06-06 11.30 | 2 | 8 | feature | 2018-06-28 09:56:36 | f7b4bab4-8009-49e8-8949-6d10542e80c4
1806081610 | 1 | 5 | 5 | 5 | 04-diss | feature | add omnibox poc page with web service for projects search | To be moved to the next month. add omnibox poc page with web service for projects search. The end goal should be pop-up omnibox which will present the results on enter lepton like... | poc-feature | ysg |  |  | 2.5 | 0.2 | feature | 2018-06-28 09:56:36 | f82419e0-ab5d-497e-bd4a-b2d9e4ffcee0
1806231402 | 3 | 5 | 5 | 4 | 02-todo | feature | add a visual indication for the active page number in the list tables view | As currently it is not exactly clear which page is the current one … The less experience is the user the more urgent this feature is … | feature | ysg | 2018-05-25 20:53 | 2018-06-30 00:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | f8655989-c240-402d-a038-0090d59b870d