## problems
id | level | seq | prio | weight | status | category | name | description | solution_proposal | owner | update_time | guid
1806102335 |  | 2 | 5 | 5 | 02-todo | setup,architecture | npm modules | the installed with npm installed modules are not transfered in the | One of those ?! : - npm install commands in the product instance install shell call ... | ysg | 2018-06-28 09:56:36 | 27443ecd-b297-4496-9ff0-85a259d8e92c
1706010100 |  | 1 | 5 | 5 | 02-todo | testing | unit controls testeing | how-to unit test ui controls | Install Joe Bergers chrome | ysg | 2018-06-28 09:56:36 | 4edcc640-e807-48c6-98c7-9c77efe8c400
1804010100 |  | 2 | 5 | 5 | 02-todo | architecture | full stack architecture definition | Gaps in the skills to define the full-stack architecture ... | Activate on those: - end-to-end testability | ysg | 2018-06-28 09:56:36 | 516ba9c6-810e-4ea1-95c0-466c5f8a369b
1805010100 |  | 2 | 9 | 9 | 09-done | testing | how-to describe the unit tests texts | The test names and descriptions should be part of the application content, linked to the requirements and userstories. | Do not describe tests at all - tests are code and they should remain code , but do describe features and functionalities with guids. | ysg | 2018-06-28 09:56:36 | 75998e69-4f17-409d-b1ec-726dcdd71716
1805172131 |  | 1 | 3 | 7 | 02-todo | testing | the long term goals are quite ambitions compared to the allocated time | The scope of the application in terms of features is enourmous compared to the available allocated time ... | Activate on those: - work smarter, not harder - attract more developers, by opennes and userfriendliness | ysg | 2018-06-28 09:56:36 | 7a0ea50e-ea2e-4b23-b271-032bec010137
1805181956 |  | 1 | 3 | 7 | 03-wip | testing | complexity is building up ... | The more complexity is added to the system the more regression bugs occur: | More : - end-to-end testing - client side JS testing | ysg | 2018-06-28 09:56:36 | 95e82e6c-7902-4141-9b5d-9b9c0aaf7506
1805070100 |  | 2 | 1 | 9 | 06-onhold | architecture | the xls is crashing all the time | use it as less as possible. Recreate it from scratch by copying only the data. And data is lost when the vm is put into sleep mode … | Activate on those: - install the phppgadmi - create web json update and insert ui - enable db-to-json - json-do-db - php-admin ?! | ysg | 2018-06-28 09:56:36 | bf648188-d98a-4ec9-b24d-5ab17c5c7c12
1805312200 |  | 2 | 2 | 8 | 02-todo | architecture | too much msgs floating around | the amount of messages becomes overwellming , one cannot be able to manage them from a central location | some kind of hash with message return code ? CallStatus type of object ?! | ysg | 2018-06-28 09:56:36 | e02fb475-ac49-4e18-81d3-fb62d4b7be26
1805171359 |  | 1 | 5 | 5 | 02-todo | performance | how-to implement minification | A lot of data is lost when the code is not minified - this is also a potential financial cost ... | Some kind of Mojo::Plugin ?! Or external plugin ... | ysg | 2018-06-28 09:56:36 | f2228fae-14d6-4e59-baf1-7da05b886058