## quinquennially_issues
id | level | seq | prio | weight | status | tags | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | update_time | guid
1806011301 | 1 |  | 5 | 5 | 03-act |  | issue-tracker | complete secured instance in the web | complete secured instance in the web: - OAuth2 , authorization and authentication - full CRUD ui for issues,projects,problems,questions,principles - history data management - time tracking biz features | goal | ysg | 2019-01-01 | 2019-06-30 | 450 | 0.1 | 2018-06-28 09:56:35.82951 | 16d59ebe-597f-40eb-b27a-bbd569d6d240
1806110013 | 1 |  | 5 | 5 | 03-act |  | issue-tracker,ui | add support for visual themes | would require a totally new approach to ui design + possibly changes to the css dir structure | milestone | ysg | 2019-01-01 | 2020-01-01 | 100 | 0.1 | 2018-06-28 09:56:35.82951 | 1bcd04c1-0556-4cb0-a4f4-0fb4a3b01de7
1806011305 | 1 |  | 5 | 5 | 03-act |  | issue-tracker | 20 users for issue-tracker projects | aquire more than 20 users to feed in data of issue-tracker prjojects | goal | ysg | 2018-06-01 | 2019-01-01 | 200 | 3 | 2018-06-28 09:56:35.82951 | 2640a904-54c8-41c4-bbab-28ab60e17bbe
1806011303 | 1 |  | 5 | 5 | 03-act |  | issue-tracker | get 10 starts and 5 pull requests | By achieving 10 stars and 5 pull requests | goal | ysg | 2018-06-01 | 2019-01-01 | 30 | 2 | 2018-06-28 09:56:35.82951 | 4bbdf412-53b5-4099-ad25-fe350b025883
1806011302 | 1 |  | 5 | 5 | 03-act |  | issue-tracker | minimalistic MVP with basic auth in the web | Deploy to an amzn instance : - minimalistic mvp with gruds and basic ui - basic auth - multiple projects | goal | ysg | 2018-06-01 | 2019-01-01 | 450 | 0.1 | 2018-06-28 09:56:35.82951 | adc249d3-7112-48aa-83f1-d9f4c8e9acf8
1806011304 | 1 |  | 5 | 5 | 03-act |  | issue-tracker | attract 2 full stack developers for collaboration | attract 2 full stack developers for collaboration | goal | ysg | 2018-05-08 | 2020-01-01 | 30 | 2 | 2018-06-28 09:56:35.82951 | d5ffbb2a-2be8-45a3-a221-72ff434eda87