## weekly_issues
id | level | seq | prio | weight | status | tags | category | name | description | type | owner | start_time | stop_time | update_time | planned_hours | actual_hours | guid
1806011701 | 1 | 5 | 5 | 5 | 07-qas | issue-tracker,setup | issue-tracker-setup | fix bug for non-aplying multiple with url params | Root cause - simple return in the wrong way of the loop | bug | ysg | 2018-06-04 21:00 | 2018-06-04 22:30 | 2018-06-28 09:56:36 | 0 | 1.5 | a1a94795-c47b-45b1-bb62-599cffedde19
1806011310 | 1 | 1 | 2 | 8 | 03-wip | issue-tracker | issue-tracker-docs | issues walktrough and user-stories doc update | As follows: - close the monthly period - move the done issues to the yearly period - move the dissed issues to the yearly period | docs | ysg | 20:00 | 21:00 | 2018-06-28 09:56:36 | 2 | 3 | a30c23d8-29e4-45cf-9f1a-d118dd25718c