## yearly_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
1805111300 | 1 | 3 | 3 | 7 | 02-todo | feature | add the create.pm web action | Create the create.pm action and integrate within the existing integration tests | activity | ysg | 2018-05-30 07:00 | 2018-06-30 07:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | 09058d4e-3759-405d-8b64-927a84023de2
1805141000 | 1 | 4 | 9 | 1 | 04-diss | docs | create user manual | create the user manual document, which will contain ONLY business rules and logic as well as non-devops related content. | docs-addition | ysg | 2018-05-25 20:53 | 2018-05-30 00:00 | 0.5 | 0.5 | ,feature | 2018-06-28 09:56:36 | 0a8d7207-09a3-47f9-a1da-d2b170e6950a
1806251545 | 1 | 5 | 9 | 3 | 02-todo | documentation | add a component diagram | Add an official component diagram UML-wise: http://agilemodeling.com/artifacts/componentDiagram.htm | task | ysg | 2018-10-01 | 2018-12-31 | 3 | 0.1 |  | 2018-06-28 09:56:36 | 0d866226-6057-4e2d-9b40-bed83c3e5d37
1804260100 | 1 | 3 | 4 | 6 | 09-done | docs | add the issue-tracker control flow diagram to the DevOps guide | And move it to the System Guide , which seems to be a more logical place Add it to the devops guide | task | ysg | 2017-09-21 07:00 | 2017-09-21 07:00 | 2 | 0.1 | docs | 2018-06-28 09:56:36 | 0f073a01-519b-4fa1-9a81-23bf63bcc9f8
1804290100 | 1 | 23 | 5 | 5 | 09-done | docs | fix nasty bug in Initiator cause by related dir in mojo testing framework | Or add the ability to resolve the dir structure of any perl script using the Initiator - obs has to be called only once ... fix nasty bug in Initiator cause by related dir in mojo testing framework. The root cause - the Initiator used $0 while it should have used __FILE__. See : https://stackoverflow.com/a/90721/65706 | task | ysg | 2018-04-29 10:21:23 | 2018-04-29 13:21:23 | 2 | 3 | docs | 2018-06-28 09:56:36 | 1395926d-3641-42a2-9e7c-390ddd6b2c1a
1805010100 | 1 | 2 | 5 | 5 | 02-todo | docs | add the Get.pm web app controller | The get controller will fetch a single item based on either on the id or the guid | task | ysg | 2017-09-21 07:00 | 2017-09-21 07:00 | 2 | 10.1 | docs | 2018-06-28 09:56:36 | 15fb3dfc-395b-4d75-b484-99fb0939533f
1805050100 | 1 | 3 | 9 | 1 | 09-done | feature | add the filter-by in url to where in db reader control flow for List.pm controller | add the filter-by in url to where in db reader control flow for List.pm controller: - ok for ok case - add nok for col does not exist | feature-implementation-implementation | ysg | 2018-05-02 10:35 | 2018-06-30 00:00 | 7 | 6 | ,feature | 2018-06-28 09:56:36 | 18b20c8b-7382-4ed1-a2eb-19d0e65b952a
1805040100 | 1 | 3 | 9 | 1 | 09-done | feature | add the pick in url to select in db reader control flow for List.pm controller | add the pick in url to select in db reader control flow | feature-implementation-implementation | ysg | 2018-05-02 10:35 | 2018-06-30 00:00 | 5 | 7 | ,feature | 2018-06-28 09:56:36 | 1beddadf-6540-45bb-8953-ffe51d19274f
1805060100 | 1 | 4 | 9 | 1 | 09-done | feature | add the order-by in url to order by in db reader control flow in List.pm controller | add the order-by in url to order by in db reader control flow in List.pm controller. Changed the format of the dat to array reference because of the need to be able to pass a sorted data structure to the render json method. | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 4 | 3 | feature, | 2018-06-28 09:56:36 | 1ec5656f-ed83-4973-a4fb-1572433d6b19
1805110401 | 1 | 4 | 5 | 5 | 04-diss | feature | add db-to-json export for all the issues tables in the integration tests | To enable later the avoidance of the xls file ... | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 4 | 0.1 | feature | 2018-06-28 09:56:36 | 22a91881-0a1d-449c-9a9d-2f53595bb35b
1805301337 | 1 | 4 | 6 | 4 | 09-done | bug | fix the NULL.md generated in generate-docs action | Due to the non availability of the relative path | bug | ysg | 2018-05-28 20:53 | 2018-05-30 00:00 | 2 | 3 | bugs | 2018-06-28 09:56:36 | 2664fcba-4399-42cd-9e4f-eb1f5f9bd38a
1806251101 | 1 | 1 | 6 | 3 | 01-eval | feature | speed-up the xls-to-db action | By running in sequence read xls , file, write to db for each table | task | ysg |  |  | 2 | 0.1 | feature,xls | 2018-06-28 09:56:36 | 34d7a771-7d09-46a4-8aa6-024d86ed4c11
1806232256 | 1 | 5 | 4 | 9 | 01-eval | feature | add modal dialog for item-edit in the list table ui | add modal dialog for item-edit in the list table ui | task | ysg | 2018-06-01 | 2018-07-30 | 50 | 2 | feature | 2018-06-28 09:56:36 | 36c176f0-b359-472a-abc0-e0a440caa92e
1805172136 | 1 | 5 | 5 | 5 | 02-todo | deployment | deploy a web accessible instance with basic authentication for demo purposes in amzn | Deploy an instance of the issue-tracker application, which will be www readable, but editable via a simple authentication. | goal | ysg | 2018-05-17 | 2018-12-30 | 20.1 | 0.1 | issuea | 2018-06-28 09:56:36 | 3750b3ff-b950-4e48-83f7-54b3eddd0d45
1805130100 | 1 | 4 | 9 | 1 | 09-done | feature | add the hide, which should pick the columns' values but not display them in the result set | add the hide, which should pick the columns' values but not display them in the result set | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 4 | 7 | feature, | 2018-06-28 09:56:36 | 3fbcf198-d24b-4d7a-b060-746c8956dc72
1805102300 | 1 | 4 | 5 | 5 | 02-todo | feature | add a default route for the "/" web address | add a default route for the "/" web address. May be something like forward to the list view ?! | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 2 | 1 | feature, | 2018-06-28 09:56:36 | 433da129-21f1-4161-9eb4-04c735d57996
1805202317 | 1 | 5 | 9 | 1 | 09-done | feature | separate the control and the page code | Add include directive in the page: - ok for add layout page - todo for add the control css from the control to the layout | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 5 | 3 | ,feature | 2018-06-28 09:56:36 | 44ae6da8-a200-40af-8eaf-a2f90ffbbab2
1805152300 | 2 | 3 | 9 | 1 | 09-done | feature | add the hide url param for the list web control | add the hide url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00 | 43280.2917 | 5 | 2 | , feature, | 2018-06-28 09:56:36 | 45bbc37d-b7e9-4ec3-a937-c8babe221c79
1806092324 | 1 | 5 | 4 | 6 | 07-qas | feature | add server side paging | Add server side paging with callable page size , and page number: - limit - | task | ysg |  | 2018-10-30 | 20 | 0.1 | architecture | 2018-06-28 09:56:36 | 45ecf793-e175-4935-ae34-70360fd65c13
1806011257 | 1 | 5 | 3 | 7 | 03-wip | feature | implement a sortable list table ui | Should be able : - to list any db table - provide the same url params as in the list labels page | feature | ysg |  | 2018-12-31 07:00 | 20 | 0.1 | feature | 2018-06-28 09:56:36 | 493ee8df-895f-4281-8ddc-2dc762dc256f
1805242250 | 1 | 6 | 5 | 7 | 07-qas | feature | create a tag cloud page | Should increaese the ability to comprehend the issues. http://mistic100.github.io/jQCloud/demo.html - refactor to factory design pattern ... | feature | ysg | 2018-06-01 | 2018-12-30 | 10 | 8 | feature | 2018-06-28 09:56:36 | 49e26dfd-a84e-4ae7-bb22-e291e1da4416
1707200100 | 1 | 23 | 9 | 1 | 02-todo | feature | implement the copy by id via the back-end api from one table to another | implement the copy by id via the back-end api from one table to another | task | ysg |  |  | 20.1 | 0.1 | ,featues,back-end | 2018-06-28 09:56:36 | 550fe1f7-9a7e-4cb6-ba57-b464e0c425a3
1805160800 | 2 | 4 | 9 | 1 | 09-done | feature | add the where url operator for quick sql liker filtering | add the where url operator for quick sql liker filtering | task | ysg | 2017-08-06 | 2017-08-07 | 15 | 0.1 | ,featues,back-end | 2018-06-28 09:56:36 | 5b3dff5e-6dab-4ac0-86d3-88aeb03db3f3
1805091300 | 2 | 5 | 6 | 4 | 02-todo | feature | create the view doc ui with vue.js | Create a simple list labels view interface which will use the list web action: - evaluete both server and client side html generation and compare performance | feature | ysg | 43280.2917 | 2018-12-31 07:00 | 0.1 | 0.1 |  | 2018-06-28 09:56:36 | 5f7cc587-aff1-408d-898d-7d66ec4acade
1805110200 | 1 | 1 | 9 | 1 | 09-done | feature | create the list page with vue.js | Create a simple list labels view interface which will use the list web action: - evaluate both server and client side html generation and compare performance - ok add error handling for missing db - add error handling for missing table - add error handling for wrong hidable column - add error handling for wrong pickable column - add error handling for wrong filterable col - add error handling for wrong col in like | feature | ysg | 43280.2917 | 2018-12-31 07:00 | 10 | 12 | ,feature | 2018-06-28 09:56:36 | 61efa941-fc1d-4269-a2c8-a6673089c60d
1805110500 | 1 | 4 | 9 | 1 | 09-done | feature | add the like-by and like-val in url to implement the like operator for filtering | add the like-by and like-val in url to implement the like operator for filtering | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 5 | 3 | feature, | 2018-06-28 09:56:36 | 65f77d91-9c65-464e-b7c9-12c71683b7dd
1806011111 | 1 | 5 | 5 | 9 | 03-wip | architure | change Front-End architecture to use Web Pack | As Web Pack seems to be the best in town package manager and a lot of JS code is distributed as npm packages. | task | ysg | 2018-06-01 | 2018-07-30 | 50 | 0.1 | architecture | 2018-06-28 09:56:36 | 6b3f9812-da36-44b9-a9ee-41f3aa599494
1805110201 | 1 | 3 | 5 | 5 | 09-done | feature | create the plain list labels view ui with vue.js | Create a simple list labels view interface which will use the list web action: - evaluete both server and client side html generation and compare performance | feature | ysg | 43280.2917 | 2018-12-31 07:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | 6d02372f-428a-42b9-852d-1cc6a350fbbc
1804300100 | 1 | 4 | 9 | 1 | 09-done | specs | define REST API response structure | Should support messages and return codes as well as data transfer. Defined : - ret - containing the http status code - msg - the msg to be passed to the client - dat - the data to be passed to the client | specs | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 1 | 2 | feature, | 2018-06-28 09:56:36 | 6e2ff438-b87e-4360-a12b-ae4d0aa42050
1805160700 | 2 | 4 | 5 | 5 | 02-todo | feature | add the feature for the validation of the spent time | design the validation of the available time and the spent time = registered time | task | ysg | 2017-08-06 | 2017-08-07 | 15 | 0.1 | feature | 2018-06-28 09:56:36 | 71c1f6df-90ef-442b-8309-6470153d50e2
1805082200 | 1 | 10 | 9 | 1 | 09-done | feature | improve integration testing | add the mysql db creation and population, add the documentation generation | feature | ysg | 2018-05-12 20:00 | 2018-05-12 21:00 | 2 | 2 |  | 2018-06-28 09:56:36 | 728b64ef-96c8-4ec4-ae64-f628c9379adf
1805110400 | 2 | 4 | 6 | 1 | 01-eval | feature | improve the select-tables web action | Add the following: - list of views - order by table name - convert result-set to array and not hash | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 00:00 | 1 | 0.1 | feature, | 2018-06-28 09:56:36 | 77481d63-7262-44cd-b80d-140ae5186ef1
1804020100 | 1 | 5 | 9 | 1 | 09-done | feature | add the web select controller | add the web select controller “ - implementation code - tests - documentation additions for : -- requirements -- userstories -- tests -- features and functionalities | feature | ysg | 2018-04-02 18:00 | 2018-05-30 22:00 | 3 | 7 | ,feature | 2018-06-28 09:56:36 | 7c5e6d72-0e83-4b0b-b80a-87e77faade5c
1805161614 | 2 | 4 | 9 | 1 | 09-done | feature | add the like-by url param for the list web control | add the like-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00 | 43280.2917 | 5 | 2 | , feature | 2018-06-28 09:56:36 | 7dfff37a-88db-4873-b928-45ebdf299b9e
1805050102 | 1 | 3 | 9 | 1 | 09-done | feature | add the filter-by in url to where in db reader control flow for List.pm controller | add the filter-by in url to where in db reader control flow for List.pm controller: - ok for ok case - add nok for col does not exist | feature-implementation-implementation | ysg | 2018-05-02 10:35:53 | 2018-06-30 00:00:00 | 7 | 6 |  | 2018-06-28 09:56:36 | 81d454b7-10a4-4c25-8a5e-a7e244bf1af3
1806232302 | 1 | 1 | 3 | 9 | 02-todo | feature | evaluate a lib for the generic forms creation | The CRUD functionality will require a generic forms creation | task | ysg | 2018-06-30 | 2018-07-15 | 5 | 0.3 | poc | 2018-06-28 09:56:36 | 82fb2eb9-9777-4977-8d5f-32fffa8d565c
1805172116 | 1 | 5 | 9 | 1 | 09-done | setup | upgrade Ubuntu 17.04->17.10 | Upgrade zesty to artful: - had to pre-install the whole perl modules package bundle - had to pre-install postgres ... Althought it would have worked probably by just installing the Perl postgres related modules. | feature-implementation | ysg | 2018-05-20 19:10:00 | 2018-05-20 23:10:00 | 0.1 | 2 | ,feature | 2018-06-28 09:56:36 | 8311dbbd-54c9-4a0c-a681-f893eb8c1853
1804020101 | 2 | 1 | 5 | 5 | 09-done | feature | add the web list controller | add the web list controller “ - implementation code - tests - documentation additions for : -- requirements -- userstories -- tests -- features and functionalities | feature | ysg | 2018-04-02 18:00 |  | 3 | 0.1 | feature | 2018-06-28 09:56:36 | 88effa07-63fa-4339-b891-6e6d95b2bd74
1805110300 | 1 | 3 | 5 | 5 | 03-act | activities | aim to use the issue tracker more on the web interface and less on the xls | In order to increase the dog food experience and provide base for the creation of issues , userstories , requirements and other specifications | activity | ysg | 2018-05-06 07:00 | 2018-12-31 07:00 | 0.1 | 0.1 | activities | 2018-06-28 09:56:36 | 89544306-4688-49e2-a175-6f74ff32962b
1805172131 | 1 | 5 | 2 | 9 | 02-todo | feature | implement data load testing | Should be single liner: - very simple - should have reliable start _time and stop_times - should be able to verify the executions times per request , request phases to keep track on performance while increasing complexity - and optionally all this by single user | goal | ysg | 2018-06-01 | 2018-07-30 | 50 | 2 | feature | 2018-06-28 09:56:36 | 8a6e2bea-a682-4c56-8dbd-b8d419c7252b
1805111000 | 1 | 4 | 9 | 1 | 09-done | setup | add the pre-loading of the env shell configuration files | the run-integration tests should pre-load the configuration file of the current instance in order to match the full environment as it is run usually. Solution : The call has to be changed to : export issue_tracker_project=""; bash src/bash/issue-tracker/issue-tracker.sh -a run-integration-tests And documented the change in the DevOps guide | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-31 17:00 | 2 | 2 | feature, | 2018-06-28 09:56:36 | 9ebb9402-fbf4-48c5-98de-9a3fceccc846
1805152200 | 2 | 2 | 9 | 1 | 09-done | feature | add the pick url param for the list web control | add the pick url param for the list web control | feature-implementation | ysg | 2017-05-14 07:00 | 43280.2917 | 5 | 2 | , feature | 2018-06-28 09:56:36 | 9fb647cc-66a0-40f4-a729-fe86f51e3ee2
1805102000 | 1 | 4 | 9 | 1 | 09-done | bugs | fix bug with non-publishing to google sheets | Due to the non-complience of the googleSheets controller with the Input-Output-Controller-Model architecture | bug | ysg | 2018-05-10 20:53 | 2018-05-30 09:54 | 0 | 1 | ,bugs | 2018-06-28 09:56:36 | a4d775f1-c0cf-4268-9862-a457dee60b97
1806110034 | 1 | 5 | 6 | 7 | 02-todo | feature | add a modal dialog edit form for the edit action | Could be either from the list as html page or from the list as lables page | task | ysg |  |  | 30 | 0.2 | ,feature,ui | 2018-06-28 09:56:36 | a5276ba4-0b12-4704-ba8a-d458ae7713e3
1806011256 | 1 | 5 | 5 | 5 | 01-eval | feature | implement a time report web ui page | The time report web ui page will : - fetch the daily,weekly,monthly and yearly hours - get the allocated hours per time period - calculate the registered actual hours to the went-by hours of the start of the period - calculate the diff between the actual and passed-by hours - accessible from the list/table-name/?as=table url - should be able t osort the data | feature | ysg |  | 2018-12-31 07:00 | 20 | 0.1 | feature | 2018-06-28 09:56:36 | a55933cd-a93a-4095-abdd-0bdfec5525af
1805152400 | 2 | 4 | 9 | 1 | 09-done | feature | add the order-by url param for the list web control | add the order-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00 | 43280.2917 | 5 | 2 | , feature | 2018-06-28 09:56:36 | ad57a078-5df1-409f-8392-136be879b8e6
1805112000 | 1 | 22 | 5 | 5 | 09-done | feature | add error handler for xls-to-db when postgres and db table does not exist | Some kind of proper error msg | bug | ysg | 2018-05-11 21:10:00 | 2018-06-11 19:20:31 | 3 | 0 | bugs | 2018-06-28 09:56:36 | b204f92d-d0f8-4573-9892-68909f3bc485
1806110020 | 1 | 5 | 3 | 6 | 03-act | security | add validation of ui params against SQL injections | Each time a new data param is to be parametrized till the db ... A validation must be added to it. | activity | ysg | 2018-06-10 23:00 | 2018-12-31 07:00 | 50 | 3 | security | 2018-06-28 09:56:36 | bdf1eaec-0d2f-454a-a0eb-4ed1d8948019
1805071500 | 1 | 4 | 9 | 1 | 09-done | feature | add the list vue.js poc | Create a proof of concept poc page with REST api fetch from the back-end using vue.js and axiom | task | ysg | 2018-05-07 13:38 | 2018-05-07 13:38 | 2 | 3 | ,feature | 2018-06-28 09:56:36 | be97faad-4c89-473c-912c-d9f583d4766a
1805222246 | 1 | 5 | 5 | 5 | 09-done | feature | add the with-col=val url param | add the with-col=val url param | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 4 | 6 | feature | 2018-06-28 09:56:36 | c434b150-df32-4de7-927f-1299b3e11b1e
1805111100 | 1 | 3 | 3 | 7 | 02-todo | feature | add the edit web action from the list as labels page | Create the update.pm action and integrate within the existing integration tests | activity | ysg | 2018-05-30 07:00 | 2018-06-30 07:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | c873496f-ec3f-4975-813d-90bde0b907bc
1805172115 | 1 | 5 | 9 | 1 | 09-done | feature | poc for client site JavaScript testing | Because if you cannot get it right from the very beginning than you will get it never ever right. implement a poc for data-load testing with single table load to postgres with start and stop times recording Add as a non-blocking post update for start_time and stop_time. Had to increase the whole OS and redo the setup install for the perl modules and the postgres because of this one ... | feature-implementation | ysg | 2018-05-16 21:10:00 | 2018-05-16 22:10:00 | 4 | 0.5 | ,feature | 2018-06-28 09:56:36 | c9455a52-6d08-4476-8838-ee2b28101575
1805312157 | 1 | 4 | 9 | 1 | 09-done | bugs | fix bug with non-informance of missing db table on xls-to-db | when the xls sheet exists but the table not now the app quites | bug | ysg | 2018-05-10 20:53 | 2018-05-30 09:54 | 1 | 1 | ,bugs | 2018-06-28 09:56:36 | cdf6fa2f-5284-4f42-8504-e75a16813d23
1805282138 | 1 | 5 | 5 | 5 | 02-todo | feature | add export to txt from web ui | add export to txt from web ui | feature-implementation | ysg |  | 2018-12-30 | 4 | 0.1 | feature | 2018-06-28 09:56:36 | d5d82d35-d291-49b3-9930-cf5f2f7bdd80
1805140900 | 1 | 5 | 9 | 1 | 04-diss | feature | poc for data-load testing | Duplicated by it-1805172136 Because if you cannot get it right from the very beginning than you will get it never ever right. implement a poc for data-load testing with single table load to postgres with start and stop times recording Add as a non-blocking post update for start_time and stop_time | feature-implementation | ysg | 2018-05-25 20:53 | 2018-06-30 00:00 | 0.1 | 0.1 | ,feature | 2018-06-28 09:56:36 | d9135812-313f-48aa-93e5-ab2573ea6a7a
1805221029 | 1 | 1 | 4 | 6 | 04-diss | feature | add form order in url params | The ability to order the form elements from the url ... By using the pick order and not a separate fo= ... | feature | ysg |  | 2018-12-30 | 3 | 0.1 | feature | 2018-06-28 09:56:36 | d9bf00a4-81c9-4bde-985f-022ccff504aa
1805070100 | 1 | 3 | 9 | 1 | 09-done | feature | add the error halding for non-existent db in List.pm controller | add the error halding for non-existent db in List.pm controller | feature-implementation-implementation | ysg | 2018-05-02 10:35 | 2018-06-30 00:00 | 0.1 | 0.25 | , | 2018-06-28 09:56:36 | dd4defef-9bdc-49f9-a4d4-3249d1ca903a
1805110600 | 1 | 3 | 5 | 5 | 02-todo | activities | publish a read-only issue-tracker MVP to a host in the cloud for demo purposes | add link to the git-hub | activity | ysg | 2018-05-06 07:00 | 2018-12-31 07:00 | 0.1 | 0.1 | activities | 2018-06-28 09:56:36 | e21a8191-c8e7-4c10-b73b-ffbb5f02f7b9
1805111400 | 1 | 3 | 4 | 6 | 02-todo | feature | create the select-create form page | To test the create action and to start avoiding using the xls | activity | ysg | 2018-05-30 07:00 | 2018-06-30 07:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | e352631e-1a3e-45d4-bdfa-40c0232eff3b
1806232301 | 1 | 1 | 1 | 9 | 07-qas | feature | add json-to-db shell action | In order to achieve independance from the xls run-time for achieving the full CRUD, I wanto to be able to take quickly backup and restore db data from files on timely basis. | task | ysg | 2018-06-23 | 2018-06-30 | 2 | 0.1 | feature | 2018-06-28 09:56:36 | eb26aeb6-1c07-47a9-b0dd-bfadd83aaf44
1805120100 | 1 | 4 | 9 | 1 | 09-done | specs | change the id's naming convention to be to hour proximity and not day only | As the day seems to be too less ... As the id's must be copieable from one table to another and quickly collisions might be created. | feature-implementation | ysg | 2018-05-10 20:53 | 2018-05-30 20:53 | 2 | 1 | feature, | 2018-06-28 09:56:36 | ecd7435f-791d-416d-b252-758d276d6e73
1805111200 | 1 | 3 | 4 | 6 | 02-todo | feature | add the select-update form page | To test the update action and to start avoiding using the xls | activity | ysg | 2018-05-30 07:00 | 2018-06-30 07:00 | 0.1 | 0.1 | feature | 2018-06-28 09:56:36 | ee0abc9f-bec6-46a8-8e16-3e051724447b
1805161613 | 2 | 4 | 9 | 1 | 09-done | feature | add the filter-by url param for the list web control | add the filter-by url param for the list web control - ok path - nok path | feature-implementation | ysg | 2017-05-14 07:00 | 43280.2917 | 5 | 2 | , feature | 2018-06-28 09:56:36 | f361339f-3647-43a4-b984-dd2c420acefb
1805282137 | 1 | 5 | 9 | 1 | 04-diss | feature | add export to xls from web ui | add export to xls from web ui | feature-implementation | ysg |  | 2018-12-30 | 4 | 0.1 | ,feature | 2018-06-28 09:56:36 | fa7be9bd-cc19-4eb4-b9a9-d8cdea2600c4
1805172135 | 1 | 5 | 2 | 9 | 02-todo | feature | implement client-side testing | By using the Mojo::Chrome module: Should be able to capture JS events: Vue induced changes on the page. | goal | ysg | 2018-06-01 | 2018-07-30 | 50 | 5 | feature | 2018-06-28 09:56:36 | fcd12d2b-50d4-441a-9fca-a6fac6234e38