## daily_issues
level | seq | prio | status | tags | category | name | description | start_time | stop_time | planned_hours | actual_hours | owner | type | guid
1 | 3 | 5 | 09-done | issue-tracker | issue-tracker | refactoring clean-up for wrapp | clean-up increase-date func, attempt to the get the new lines output in the doRunCmdOrExit func | 10:00 | 10:30 | 1.33 | 0.5 | ysg | task | 6e66b70a-04d0-429f-ade7-39af3412f783
1 | 6 | 2 | 07-qas | issue-tracker | issue-tracker-features | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | 10:40 | 11:00 | 1.33 | 0 | ysg | task | c8b9337b-3065-4c03-a3b7-11806583a6e8

## weekly_issues
level | seq | prio | status | tags | category | name | description | start_time | stop_time | planned_hours | actual_hours | owner | type
1 | 5 | 3 | 05-test | issue-tracker | issue-tracker | clone issue-tracker project from another one | clone issue-tracker project from another one | 2017-07-27 21:30 | 2017-07-27 22:00 | 4 | 1 | ysg | activity
1 | 1 | 3 | 04-diss | issue-tracker | issue-tracker | poc for write table to conluence page | poc for write table to conluence page |  |  | 2 | 8 | ysg | task
1 | 6 | 4 | 03-wip | issue-tracker | issue-tracker-features | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | 2017-08-20 10:40 | 2017-08-20 11:00 | 1.3333 | 0 | ysg | task
1 | 3 | 5 | 09-done | issue-tracker | issue-tracker | refactoring clean-up for wrapp | clean-up increase-date func, attempt to the get the new lines output in the doRunCmdOrExit func | 10:00 | 10:30 | 1.33 | 0.5 | ysg | task
1 | 6 | 2 | 07-qas | issue-tracker | issue-tracker-features | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | 10:40 | 11:00 | 1.33 | 0 | ysg | task

## monthly_issues
level | seq | prio | status | tags | category | name | description | owner | type | start_time | stop_time | planned_hours | actual_hours
1 | 6 | 2 | 09-done | issue-tracker | issue-tracker-features | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | ysg | task | 10:40 | 11:00 | 1.33 | 0
1 | 25 | 9 | 09-done | issue-tracker | issue-tracker | imporove the error handling in run-pgsql-scripts | imporove the error handling in run-pgsql-scripts | task | ysg | 2017-10-04 19:30 | 2017-10-04 21:30 | 2 | 1
1 | 12 | 6 | 01-eval | issue-tracker | issue-tracker-features | gsheet-to-db feature | implement read from google sheeet in issue-tracker for any issue--tracker project | task | ysg | 2017-08-14 00:00 | 2017-08-30 19:30 | 3.5 | 0
1 | 9 | 5 | 06-onhold | issue-tracker | issue-tracker-features | implement mysql nested-set load | the isg-pub mysql nested-set load has been real time burner. implement mysql nested-set load by setting left_rank and right_rank into the hs | task | ysg | 2017-10-03 08:16 |  | 1.33 | 0
1 | 9 | 4 | 07-qas | issue-tracker | issue-tracker-features | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | task | ysg |  |  | 1.33 | 0
1 | 10 | 5 | 02-late | issue-tracker | issue-tracker-docs | publish the issue-tracker xls to google sheet | publish the issue-tracker xls to google sheet - set world view permisssion !!! | activity | ysg |  |  | 2 | 0
1 | 13 | 6 | 01-eval | issue-tracker | issue-tracker-features | publish all the issue-tracker events into the google sheet calendar | publish all the issue-tracker events into the google sheet calendar | task | ysg |  |  | 30 | 0
1 | 19 | 8 | 03-act | issue-tracker | issue-tracker-features | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | task-ondemand | ysg |  |  | 2.5 | 0
1 | 25 | 9 | 09-done | issue-tracker | issue-tracker | imporove the error handling in run-pgsql-scripts | imporove the error handling in run-pgsql-scripts, improve the error handling in the main.pl script | task | ysg | 2017-10-04 19:30 | 2017-10-04 21:30 | 2 | 1

## yearly_issues
level | prio | status | category | name | description | owner | type | start_time | stop_time | planned_hours | actual_hours
2 | 6 | 01-eval | issue-tracker-features | integration with google calendar | integration with google calendar | ysg | task | 2017-10-01 | 2017-12-31
2 | 5 | 02-todo | issue-tracker-system | add web framework app layer | add web framework app layer | ysg | task | 2017-06-23 | 2017-12-31
2 | 5 | 02-todo | issue-tracker-system | start combining isg-pub and issue - tracker | start combining isg-pub and issue - tracker | ysg | task | 2017-10-01 | 2017-12-31
2 | 5 | 02-todo | issue-tracker-features | implement 2 -> 7 -level nesting for all actions | implement 2 -> 7 -level nesting for all actions | ysg | task | 2017-10-01 | 2017-12-31
2 | 6 | 02-todo | issue-tracker-features | integration with isg-pub | integration with isg-pub | ysg | task | 2017-10-01 | 2017-12-31
2 | 1 | 03-act | issue-tracker-maintenance | achieve minimalistic maintenance | achieve minimalistic maintenance | ysg | task | 2017-12-31 | 2017-12-31
2 | 1 | 03-act | issue-tracker-system | scalability: operate more than 15 - 20 projects | operate more than 15 projects in production mode | ysg | task | 2017-11-01 | 2017-12-31
2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | ysg | task | 2017-03-01 | 2017-12-31
2 | 5 | 03-act | issue-tracker-bugs | keep the amount of bugs on monthly basis to less than 5 | keep the amount of bugs on monthly basis to less than 5 | ysg | activity | 2017-03-01 | 2017-12-31
2 | 4 | 07-qas | issue-tracker-features | implement the gmail-txt-issues action | implement the gmail-txt-issues action | ysg | task | 2017-06-12 | 2017-06-15
2 | 5 | 07-qas | issue-tracker-features | add issues sorting by any attribute for any action | add issues sorting by any attribute for any action | ysg | task | 2017-12-31 | 2017-12-31
2 | 5 | 07-qas | issue-tracker-features | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | implement daily handling of issues, notes , cheatsheets and input xls for mulitple projects | ysg | task | 2017-12-31 | 2017-12-31
2 | 4 | 09-done | issue-tracker-features | implement 2-level nesting for all actions | implement 2-level nesting for all actions | ysg | task | 2017-03-01 | 2017-10-01
2 | 5 | 09-done | issue-tracker-features | add the txt-to-db and db-to-xls action | add the txt-to-db and db-to-xls action | ysg | task | 2017-03-01 | 2017-12-31
2 | 5 | 09-done | issue-tracker-features | add the xls-to-db and db-to-txt action | add the xls-to-db and db-to-txt action | ysg | task | 2017-03-01 | 2017-12-31

## quinquennially_issues
level | seq | prio | status | tags | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours
2 | 9 | 1 | 03-act | issue-tracker | issue-tracker | 20 users for issue-tracker projects | aquire more than 20 users to feed in data of issue-tracker prjojects | ysg | goal | 2018-06-01 | 2019-01-01 | 0 | 0
2 | 9 | 1 | 03-act | issue-tracker | issue-tracker | gain github popularity for the issue-tracker project | By achieving 10 stars and 5 pull requests | ysg | goal | 2018-06-01 | 2019-01-01 | 0 | 0

## decadally_issues
level | prio | status | category | name | description | type | owner | start_time | stop_time
2 | 4 | 03-act | issue-tracker-design | achieve simplistic design and ease to use | achieve simplistic design and ease to use | goal | ysg | 2017-03-01 | 2017-12-31

## questions
level | seq | prio | status | tags | category | name | description | solution_proposal | updated_by | owner
1 | 1 | 1 | 03-wip | issuee-tracker | issuee-tracker | how-to copy efficiently items rows froom one project to another | the copy of items data from one project to another includes the copying via ui ( google sheet , xls ) | so far via ui - in Excel use paste special, values , so that the formattig stays the same. After the upsert with guid's if an issue is trully portable than it could be tracked from different projects | ysg | ysg
1 | 1 | 1 | 02-todo | issuee-tracker | issuee-tracker | how-to copy autogenerated data | we know how-to copy the non-autogenerated data from src db to another , yet has to copy it with the autogenerated uuid's | _ | ysg | ysg

## problems
level | seq | prio | status | category | name | description | solution_proposal | updated_by | owner | parent_id
1 | 1 | 1 | 03-wip | georgievi-fina | manual formatting | too much time is burning the manual formatting of the google sheets … | yet once formatted obviously even on post via the api the formatting persists | ysg | ysg