## monthly_issues
id | level | seq | prio | status | tags | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | update_time | guid
180213 | 2 | 1 | 1 | 07-qas | issue-tracker | issue-tracker-features | run the xls-to-db in rdbms_type=mysql and load_model=nested-set against isg-pub | run the xls-to-db in rdbms_type=mysql and load_model=nested-set against isg-pub | task | ysg | 2018-02-13 16:30 | 2018-02-13 19:15 | 30 | 0 | 2018-02-14 22:17:18.598948 | e7001484-bbe1-4376-bcb1-abee7814a0aa
180126 | 2 | 1 | 4 | 07-qas | issue-tracker | issue-tracker-features | impelement hsr2 to hierarchical hsr2 converter module | impelement hsr2 to hierarchical hsr2 converter module to read from the xls reader and to write to the db writer | task | ysg | 2018-02-01 | 2018-02-28 | 30 | 0 | 2018-02-14 22:17:18.598948 | b2f70235-ddfc-4407-9dbf-ff18b9246cdd
180201 | 2 | 3 | 2 | 05-tst | issue-tracker | issue-tracker-features | implement xls-to-db for mysql hierarchichal load via the Model | implement xls-to-db for postgres hierarchichal load via by passing the objModel | task | ysg | 2018-02-01 | 2018-02-28 | 30 | 0 | 2018-02-14 22:17:18.598948 | 86331450-8729-4e22-9637-8f185096175d
180301 | 1 | 3 | 2 | 02-todo | issue-tracker | issue-tracker-features | implement xls-to-db for postgres hierarchichal load via the Model | implement xls-to-db for postgres hierarchichal load via the Model | task | ysg | 2018-02-01 | 2018-02-28 | 30 | 0 | 2018-02-14 22:17:18.598948 | 694673b5-9a80-40d6-b5d8-7692f99770be
180101 | 1 | 6 | 5 | 03-act | issue-tracker | issue-tracker | implement IOCM architecture | Create an Architecture document in the issue-tracker which defines the IO MVC architecture: | activity | ysg | 2018-01-01 | 2018-01-30 |  |  | 2018-02-14 22:17:18.598948 | bca9c15b-1d7d-492e-9d14-84bf4401895c
160101 | 1 | 8 | 2 | 05-tst | issue-tracker | issue-tracker | implement mysql nested-set load | the isg-pub mysql nested-set load has been real time burner. implement mysql nested-set load by setting left_rank and right_rank into the hs | task | ysg | 2017-10-03 08:16 |  | 1.33 | 0 | 2018-02-14 22:17:18.598948 | 71824118-d683-47a8-a754-f5dfb6bc2cf9
171212 | 1 | 9 | 5 | 07-qas | issue-tracker | issue-tracker | change the issue-tracker setup for code and data accessibility from host and vms | change the issue-tracker setup for code and data accessibility from host and vms Implement via symlink under /opt/csitea/issue-tracker Benefits - less work during publishing , can access both code and data via mac host's UI | task | ysg | 2017-10-03 08:16 |  | 1.33 | 0 | 2018-02-14 22:17:18.598948 | 775d7bfb-a03e-4b37-9163-93d157ec0302
171223 | 1 | 10 | 5 | 07-qas | issue-tracker | issue-tracker | add unit tests for the "platform" modules | add unit tests for the "platform" modules : - Initaitor - Configurator - Dispatcher - Logger | task | ysg | 2017-10-03 08:16 |  | 1.33 | 0 | 2018-02-14 22:17:18.598948 | 3a6df1be-d322-4c10-b710-c41030315307
170810 | 1 | 12 | 5 | 01-eval | issue-tracker | issue-tracker | publish all the issue-tracker events into the google sheet calendar | publish all the issue-tracker events into the google sheet calendar | task | ysg | 2017-08-10 |  | 30 | 0 | 2018-02-14 22:17:18.598948 | 2c18c4fc-76d9-47cf-b3e5-4c1a321a1c84
170608 | 1 | 13 | 7 | 06-onhold | issue-tracker | issue-tracker | add load-meta-to-json action | add load-meta-to-json action | task | ysg |  |  | 10 | 2 | 2018-02-14 22:17:18.598948 | f92cc159-d468-4fde-af73-6e2e5607d418
170530 | 1 | 17 | 6 | 01-eval | issue-tracker | issue-tracker | gsheet-to-db feature | implement read from google sheeet in issue-tracker for any issue--tracker project | task | ysg | 2017-08-14 00:00 | 2017-08-30 19:30 | 3.5 | 0 | 2018-02-14 22:17:18.598948 | 9e63bb7e-52f6-49d1-8358-41d17aeae3a2
180119 | 1 | 19 | 6 | 03-act | issue-tracker | issue-tracker-functionalities | impelement the SetGetable and AutoLoadable for the rest of the Perl OO Modules | Implement the SetGettable interface Implement the Autoloadable interface | activity | event | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0 | 2018-02-14 22:17:18.598948 | 8d63033c-c39f-4c35-883b-d87f0884bb92
180123 | 1 | 22 | 6 | 06-onhold | csitea-biz | issue-tracker | implement the passing of the objModel for all the actions | since, from the yearly report found out that too much time was spent on activities which did not fly ... | task | ysg | 2018-02-01 | 2018-02-28 |  |  | 2018-02-14 22:17:18.598948 | 14104a92-d2f6-414d-a1b4-c64dae23644e
170518 | 1 | 28 | 6 | 07-qas | issue-tracker | issue-tracker | implement upsert in DbWriterPostgres | implement upsert in DbWriterPostgres so that if there is a column in the has ref which is named guid and the insert fails update the value for the row. | task | ysg |  |  | 1.33 | 0 | 2018-02-14 22:17:18.598948 | 07375ef0-03b2-41f3-af3c-55b8ab4c38f4
180205 | 1 | 30 | 7 | 06-onhold | issue-tracker | issue-tracker | apply the interfaces for the most common methods in the perl code | applied to several : TestInitiator.pl TestConfigurator.pl TestMdlHsr2.pl TestLogger.pl TestSetGetable.pl TestAutoLoadable.pl TestDispatcher.pl | task | event | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0 | 2018-02-14 22:17:18.598948 | 8b0b8b2c-06e0-4642-b30b-e00e7206fbfa
171224 | 1 | 33 | 8 | 07-qas | issue-tracker | issue-tracker | add implementation for the interfaces for the most common methods in the perl code | Implement the SetGettable interface Implement the Autoloadable interface | task | event | 2018-01-19 21:00 | 2018-01-21 21:00 | 1.5 | 0 | 2018-02-14 22:17:18.598948 | 7b78e5f0-9884-4be5-a045-bda965907744
170606 | 1 | 35 | 8 | 09-done | issue-tracker | issue-tracker | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | clone a src issue-tracker daily dir into a tgt issue-tracker project daily dir | task-ondemand | ysg |  |  | 2.5 | 0 | 2018-02-14 22:17:18.598948 | 672a0083-b2d4-4b16-97fa-ad1e551ce05f