## monthly_issues
id | level | seq | prio | weight | status | category | name | description | type | owner | start_time | stop_time | planned_hours | actual_hours | tags | update_time | guid
180802130001 | 2 | 3 | 5 | 7 | 09-done | feature | add the create back-end web action | Create the create.pm action and integrate within the existing integration tests | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 16:36:41 | 0c5310cf-b831-429b-9e2d-cfa43ec9561c
180710102901 | 1 | 1 | 4 | 8 | 07-qas | feature | add the CREATE for the CRUD table via a single click in etable | via a single click in the e-table: - wip for add the button ui - ok for click inserts into db - wip for fetch new item data | feature | ysg | 2018-07-03 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 16:35:35 | 1a7d9625-dc18-4857-8544-8cda8446b4a3
180801133401 | 1 |  | 5 | 9 | 09-done | bug | clean-up all the console.log from the list-etablet template | All the console.log statements should be cleaned | refactor | ysg | 2018-06-26 10:00:00 | 2018-06-29 11:00:00 | 4 | 0.1 | feature | 2018-08-06 16:36:08 | 32ea2947-5e1e-4dba-aa06-1826e881406c
180517213101 | 1 |  | 3 | 9 | 02-todo | load-testing | add load testing to the update back-end web action | By simply instantiating ASYNCRONOUSLY 2,4,16,32,64,128,256,512,1024 ajax calls at once non-blocking-wise . Chk the following info src: https://mojolicious.io/blog/2017/12/09/day-9-the-best-way-to-test/ http://blogs.perl.org/users/chase_whitener/2016/01/mock-testing-web-services-with-mojo.html | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 2 | feature | 2018-08-06 16:35:05 | 3ad4356d-1334-4d99-b300-9d5e45f55715
180802110002 | 2 |  | 6 | 5 | 01-eval | feature | select all the txt on focus during inline-cell-edit | or consider it not part of MVP and use simply Ctrl + E short cut workaround … chck the following info-src: https://stackoverflow.com/questions/6139107/programmatically-select-text-in-a-contenteditable-html-element | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 3 | 0.1 | feature | 2018-08-06 16:36:24 | 46b840ed-8445-4706-99b0-b0530c40d61c
180803092710 | 1 |  | 4 | 6 | 02-todo | documentation | shorten the README.md | Тhe README.md is too broad - should be shorten : - remove the installation stuff … - fix all the grammar mistakes !!! | task | ysg | 2018-08-03 09:27:42 | 2018-08-30 22:00:00 | 1 | 0.1 | documentation | 2018-08-06 16:35:38 | 4991fb7b-fd29-4dbf-a502-95df05e4aa8f
180802130101 | 1 | 4 | 4 | 7 | 02-todo | feature | add the delete back-end web action | delete the delete.pm action and integrate within the existing integration tests | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 16:35:32 | 4e96fd0c-fbea-497d-ab27-08e107032f8e
180806125916 | 1 |  | 2 | 9 | 02-todo | bug | the inline-cell update removes the new lines from the cell | the inline-cell update removes the new lines from the cell | task | unknown | 2018-08-06 12:59:16.274161 | 2018-08-06 12:59:16.274161 | 1 | 0.1 |  | 2018-08-06 16:30:21 | 50dcc5c8-99ba-4ca0-8f90-024d36181918
180802105623 | 1 |  | 3 | 9 | 09-done | release | release v0.4.6 | Couple of small fixes in the integration tests ... release v0.4.6 should be considered "transitional" release as it contains only the update of the CRUDS feature, although there is some need for refactoring and additional testing the "create " and "delete" features must be added asap to avoid wasting time with additional tools and Excel. Also this should be the first release to be released to the cloud as well. | task | ysg | 2018-08-02 10:56:49 | 2018-08-05 22:56:49 | 3 | 0 | release | 2018-08-06 16:35:34 | 54263c81-3eee-4104-bb2a-d64ceeb7cc14
180806112810 | 1 |  | 4 | 4 | 09-done | feature | add automatic addition of the update_time via trigger for all tables having the update_time attribute | add automatic addition of the update_time via trigger for all tables having the update_time attribute | task | ysg | 2018-08-06 11:15:48.325569 | 2018-08-06 11:15:48.325569 | 1 | 1.5 | feature | 2018-08-06 16:35:38 | 6bacb384-93cf-4aa0-b4cf-4f31365cd39e
180806125535 | 2 |  | 2 | 9 | 03-wip | documentation | update the docs for the CREATE in CRUDS feature: - update the Features and Functionalities Guide - update the System Guide ( logic for the update ) - update the Requirements - update the UserStories | update the docs for the CREATE in CRUDS feature: - update the Features and Functionalities Guide - update the System Guide ( logic for the update ) - update the Requirements - update the UserStories | task | unknown | 2018-08-06 12:55:35.853206 | 2018-08-06 12:55:35.853206 | 3 | 1.1 |  | 2018-08-06 16:35:14 | 77ed6c44-c3b2-447b-8f6b-1ce087a9175b
180717013001 | 1 |  | 4 | 9 | 02-todo | refactoring | remove the run-logging | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 16:35:42 | 853ae954-3cac-4638-ad55-ddd07799b893
180806163116 |  |  | 5 | 9 | 09-done | feature-bug | add proper error handling on insert of duplicate id's |  | task | unknown | 2018-08-06 16:30:34 | 2018-08-06 16:30:34 | 0.1 | 4 |  | 2018-08-06 16:36:23 | 872e18f3-3cb4-4b18-830e-81c141ba6841
180806125917 | 1 |  | 1 | 9 | 02-todo | feature | Change the background on the editable on focus | Change the background on the editable on focus | task | unknown | 2018-08-06 12:59:17.629376 | 2018-08-06 12:59:17.629376 | 0.5 | 0.1 |  | 2018-08-06 16:34:40 | 8bc4bb63-3cbd-443b-943f-98df49931ca2
180802130102 | 2 | 5 | 2 | 7 | 02-todo | feature | add the delete vue button component poc | Add a poc page with a custom vue button component demonstrating the following: - ability to instantiate multiple independant instances of the button - ability to assign different id's to the buttons - ability to present dialog box with ok and cancel after the clicking of the button - ability to perform an AJAX call after pressing the button - ability to perform an AJAX call after pressing the ok | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 0.1 | feature | 2018-08-06 16:30:21 | 8beddcb3-bcd6-4292-bdc4-f79c73744ca1
180517213501 | 1 |  | 4 | 9 | 02-todo | feature | implement client-side testing | By using the Mojo::Chrome module: Should be able to capture JS events: Vue induced changes on the page. | goal | ysg | 2018-06-01 00:00:00 | 2018-07-30 00:00:00 | 50 | 5 | feature | 2018-08-06 16:35:40 | 97e139e7-1af4-4049-997d-f57d219072bb
180801152124 | 1 |  | 6 | 9 | 09-done | refactoring | add a check for the generated md docs to have more than 100 lines | add a check for the generated md docs to have more than 100 lines | task | ysg | 2018-08-01 14:15:36 | 2018-08-01 14:15:36.853822 | 1 | 1 | feature | 2018-08-06 16:36:26 | a1760383-272f-495d-b12a-4f905114d7d1
180802130002 | 2 | 2 | 9 | 7 | 09-done | feature | add the create vue button component poc | Add a poc page with a custom vue button component demonstrating the following: - ok hardcode the id of the button , make it part of the table - ok onclick event prints the id into the console - ok ability to perform an AJAX call after pressing the button from the parent el - ok - ability to generate the id in the yymmddHHMMSS format - ok - ability to pass the id to the back-end ajax call as the - ok - grasp the child to parent event and data flow : https://stackoverflow.com/a/40915910/65706 | task | ysg | 2018-08-02 10:56:49 | 2018-06-30 07:00:00 | 0.1 | 1 | feature | 2018-08-06 16:36:31 | b384324d-e883-4d43-ad4f-f67c7f649343
180806163114 |  |  | 5 | 9 | 09-done | feature | add keyboard scrolling via the selectability of the id's |  | task | unknown | 2018-08-06 16:30:32 | 2018-08-06 16:30:32 | 1 | 0.2 |  | 2018-08-06 16:36:14 | b7e9aa03-ade4-4519-a3dd-b0eb6c6e970c
180801151524 | 1 |  | 5 | 9 | 04-diss | refactoring | No relevant anymore ... Refactor the edit web action to reflect the vue page life cycle | As shown in the following diagram:info-src: https://vuejs.org/v2/guide/instance.html#Lifecycle-Diagram | task | ysg | 2018-08-01 14:15:36 | 2018-08-01 14:15:36.853822 | 4 | 10 |  | 2018-08-06 16:35:56 | cf0e5c9c-c84c-4855-92f0-a4ad7244ac24
180717013101 | 1 |  | 5 | 9 | 09-done | bug | fix the bug "for updating the cell content in table inline edit on error, while it shouldn't" | related to the it-180801151524 ... this is more of a generic question - how-to keep in sync the client-side and server side data structures - perhabs must update the client side array too ?!After the user updates the cell conent the post fires, the error msg is displayed but the content stays changed while it is not changed in the db … which is misleading … The behaviour should be changed so that the content will preserve its original state ... | bug | ysg | 2018-07-17 00:00:00 | 2018-07-17 02:00:00 | 50 | 8 | feature,msg | 2018-08-06 16:35:51 | e77b0330-348f-47e6-82b4-8a2900d173cc
180717013201 | 1 |  | 3 | 9 | 02-todo | bug | remove the unneeded run-logging | There is run-logging which is not used anymore - to remove | bug | ysg | 2018-07-17 00:00:00 | 2018-07-30 00:00:00 | 50 | 8 | feature,CRUD | 2018-08-06 16:35:30 | f45c5696-4f2e-448d-bf86-2b655cef82eb